| Datix ID | Portfolio | Risk Domain (Strategic Objective) | Risk Title | Risk Description | Controls in place | Action Plan | Sources of Assurance | Rating (current) | Rating (Target) | Trend | Opened | Review date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4260 | Chief Ambulance Services Commissioner | Set the Strategic Commissioning direction | Failure to produce agreed Commissioning Frameworks and Commissioning Intentions | IF: There is a failure to produce and agree Commissioning Frameworks and commissioning intentions Then: The commissioned providers would not be clear regarding expectations for the quality, effectiveness and efficiency of services within an agreed financial plan. Resulting in: Lack of clarity in the direction of the commissioned organisations (WAST and EMRTS) | - Ensuring a programme approach to developing commissioning frameworks for delivery with focus on monitoring progress through the EASC Sub Groups - Commissioning Intentions collaboratively developed and agreed with quarterly updates to be provided - Forward look developed for all EASC Sub Groups including receiving progress on the deliverables within the plans - Regular reporting of the Commissioning Update from EASC Sub Groups to the EAS Joint Committee on progress - Commitment from the EASC for commissioning cycles - EMS Commissioning Framework refreshed - Local integrated commissioning action plans developed by HBs and WAST, process supported by EASC Team and regularly updated - Ambulance improvement plan developed and circulated weekly | EASC Commissioning Cycle in place to set out the process and timeline for the development of Commissioning Intentions and Commissioning Frameworks; Commissioning Intentions agreed for EMS, NEPTS and EMRTS monitored at each EASC Management Group (bi- monthly) meeting and with quarterly updates to EASC; Commissioning Frameworks enacted for all commissioned services, Refreshed Emergency Ambulance Services Commissioning Framework agreed at September EASC meeting Three key actions with appropriate indicators agreed with each HB during the winter period | - EASC Commissioning Cycle - EASC Commissioning Intentions - Commissioning Frameworks – reported to EASC every meeting (quarterly information) - Minutes of EASC Sub Group meetings monitoring progress against plans - Quarterly updates against EASC IMTP and Commissioning Intentions and EASC IMTP tracker | 4x1 = 4 | CXL 4x1=4 |  | 01/08/2020 | Reviewed January 2024 To review July 2024 To remain on risk register |
| 4502 | Chief Ambulance Services Commissioner | Meet the Ministerial direction to produce an EASC IMTP | Failure to develop an agreed EASC IMTP for endorsement by the Joint Committee seeking approval from the Welsh Government | IF: There is no agreement for the EASC IMTP Then: The Commissioning Frameworks and Commissioning Intentions would not be supported Resulting in: Lack of clarity in the direction of the commissioned organisations (WAST and EMRTS) | - CASC Quality and Delivery meeting held monthly to discuss quality and performance matters - Detailed work to deliver EASC IMTP overseen by EASC Management Group •EASC IMTP (2023 to 2026) approved by EASC (2023) - EASC IMTP Quarterly update reports via EASC Commissioning Update reports to EASC - CASC IQPD (Integrated Quality and Performance Delivery) meeting with Welsh Government bi-monthly - CASC meetings with Welsh Government planning department - EASC IMTP 2023-26 confirmed as acceptable (with accountability conditions) by Welsh Government with quarterly updates in-year - IMTP tracker in use | EASC IMTP submitted to WG Awaiting response Quarterly updates to be provided IMTP Tracker developed for overall EMS performance ambitions | - Consistency between EASC IMTP with WAST IMTP and also with Health Boards - Awaiting letter of support from the Welsh Government - EASC Approval of the plan •Quarterly IMTP updates to EASC and its sub groups and EASC IMTP Tracker | 4x1=4 | CXL 4x1= 4 |  | 01/08/2020 | Reviewed July 2023 Next review April 2024 To remain on Risk Register |
| 4503 | Chief Ambulance Services Commissioner | Effective Commissioning | Failure to deliver the Ministerial direction that EASC effectively plans, commissions and secures services within its remit; and failure to maintain collaborative relationship with providers | IF: The EASC fail to plan and secure services and maintain effective collaborative relationships with providers Then: The purpose and effectiveness of the EAS Joint Committee would not be met Resulting in: Potential Ministerial and Welsh Government intervention | - Agreed collaborative commissioning methodology; whole system approach with key stakeholders - Review and refine commissioning arrangements and refresh Commissioning Frameworks - Effective function of the EASC Joint Committee - Independent Chair - Effective governance arrangements in place - CASC and Welsh Government IQPD meetings (bi-monthly) •Minister meets with the Chair and CASC quarterly - Meet regularly with providers to ensure continued development of open and transparent relationship - Ministerial Summit meeting on Handover Improvement plans (as a result of increasing numbers of hours lost) - Committee reviews its effectiveness annually – undertaken in May 2023 – no specific areas of concern identified re commissioning - Chair and CASC annual visits with all health boards in Wales planned - Ambulance improvement plan developed, agreed and circulated weekly | - Commissioning framework and monitoring at EASC and its sub groups - Annual Governance Statement produced - Monitoring of EASC IMTP at EASC and sub groups - Review and refine governance arrangements - Maintaining close working and collaborative relationships during unprecedented system pressures - EASC action plan for Ministerial priorities and monthly monitoring return commitment including Integrated Commissioning Action Plans - Three key actions with appropriate indicators agreed with each HB during the winter period Improvement plans are used by EASC Team, NHS Executive and WG for focus and consistent approach | - Internal and external audit •Welsh Government - EASC Committee members - Annual Governance Statement •Strategic Commissioning intentions and Commissioning Frameworks - Continued engagement with the commissioning process and EASC Governance - EASC Action Plan with monthly update - Chair's appraisal letter with Minister | 5x3=15 | CXL 5x1=5 |  | 01/08/2020 | Reviewed January 2024 Review April 2024 Plan – IMTP Commission – Quality and Delivery Frameworks Secure – via organisation WAST / EMRTS Work together collaboratively through EASC governance mechanisms |
| 4504 | Chief Ambulance Services Commissioner | Outcome measurement | Failure to respond to requirements identified within commissioned work related to the ambulance services | IF: Work commissioned is failed to be acted upon Then: risks and issues identified will not be acted upon and implemented Resulting in: a missed opportunity to improve services for patients leading to harm | - Forward plan (Annual Business Plan) for EASC and all sub groups - Development of action plans which are received, endorsed and approved by the EASC for action - Action log for EASC and all sub groups - Regular review of Ambulance Service Indicators and publication of ASIs - Commissioning intentions - including measurement across the system - Commissioner request for system wide measures - Ongoing refresh of the Commissioning Frameworks - Integrated Commissioning action plans supporting health boards to commission the required ambulance services for their populations | - Governance and planning for EASC and all sub groups and supporting meetings - Reviews of the commissioning frameworks - EASC Action Plan and monthly monitoring return commitment - Work with providers and their partners to ensure services are delivered in line with the expectations of the joint Committee - Monthly ICAP meetings and overview report | - Amber Review •ORH Report D&C •Emergency Ambulances Framework - updated Sept 2022 - McClelland Review of Welsh Ambulance Services (2013) - Internal and external audit - CASC IQPD meetings with Welsh Government - Annual Governance Statement - New D&C for EMS planned to start - D&C for NEPTS services completed - ICAP report to EASC / AR Committee | 4x3=12 | CXL 4x2 = 8 |  | 01/08/2020 | Reviewed October 2023 Next review April 2024 |

| Datix ID | Portfolio | Risk Domain (Strategic Objective) | Risk Title | Risk Description | Controls in place | Action Plan | Sources of Assurance | Rating (current) | Rating (Target) | Trend | Opened | Review date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4505 | Chief Ambulance Services Commissioner | Ministerial direction | Failure to achieve the agreed Chair's objectives with the Minister | IF: The agreed Chair's objectives with the Minister are not delivered Then: Then the confidence of the Minister will be potentially compromised Resulting in: The Minister not being assured that necessary progress has been made in the commissioning of ambulance services and the wider connections to unscheduled care services in Wales | •Regular meetings with the EASC team to discuss any issues as well as quality issues and the development of improved reporting arrangements - Cross reference to the work to deliver the Six Goals for Urgent and Emergency Care Programme and particularly Goal 4 | - Commissioner support for commissioning - EASC Commissioning intentions - Refresh Commissioning Frameworks - EASC IMTP - 'Focus on' sessions at EASC to discuss wider system issues - Review term of office – 31 October 2023 – extended to 31 March 2024 | - Minister's response following Chair's appraisal - Six Goals for Urgent and Emergency Care Programme delivery particularly Goal 4 - Updated objectives for Chair received Oct 2023 | 3x2=6 | CXL 3 x2 = 6 |  | 01/08/2020 | Reviewed October 2023 Next review April 2024 To remain on risk register |
| 4506 | Chief Ambulance Services Commissioner | Securing safe ambulance services | Failure to achieve agreed performance standard for category red calls which is 65% of calls responded to within 8 minutes | IF: The red performance level is less than 65% response rate within 8 minutes across Wales as a whole on a monthly basis Then: The core target will be missed Resulting in: Unsatisfactory service for the people of Wales (or within specific health board areas) with increased likelihood of harm, disability and death. | - The necessary resources secured in the EASC IMTP - Performance monitoring on a daily basis and month to date position - Bi monthly CASC IQPD meetings with Welsh Government - CASC monthly Quality and Delivery Meeting with the Welsh Ambulance Services NHS Trust - Commissioner element of EMS Demand and Capacity plan for additional staff supported – implementation being monitored - Quality and Safety Report presented at every EASC meeting - Commissioner element of EMS Demand and Capacity plan for additional staff supported – implementation being monitored - Quality and Safety Report presented at every EASC meeting - Commissioner element of EMS Demand and Capacity plan for additional staff supported; - Commissioned a new demand and capacity review (August 2023) - Financial commitment to maintain overtime for WAST staff (Sept 2023) - Ambulance improvement plan developed, agreed and circulated weekly | - Delivery of EASC IMTP and WAST IMTP - Implementation of the commissioning intentions through the commissioning agreement - Role of the EASC Management Group to provide oversight on operational performance - Development of WAST performance improvement plan - EASC Action Plan includes detailed clinical review of red incidents to understand clinical need of patients to assess improvement opportunities - ICAP meetings and monitoring commitments and deliver - Three key actions with appropriate indicators agreed with each HB during the winter period - Improvement plans are used by EASC Team, NHS Executive and WG for focus and consistent approach | •Ambulance Service Indicators - Daily weekly and monthly performance reports - Remedial Action plans (if required) - Specific targeted actions as required - Implementation of the new Demand and Capacity Review - EASC Action Plan - CASC liaison with Chief Operating Officers - Agreement to maintain front line capacity which will also support the Cymru High Acuity Response Unit (CHARU) | 5x5=25 | CXL 5x3= 15 |  | Aug-20 | Reviewed January 2024 Next review April 2024 Closely monitored – daily and weekly dashboard Until target met, to remain at score 25 |
| 4507 | Chief Ambulance Services Commissioner | Securing safe ambulance services | Failure to achieve agreed performance for amber category calls | IF: The average and longest times for amber incidents do not reduce Then: Patients will not receive the care they need in a timely manner Resulting in: unsatisfactory service for the people of Wales (or within specific health board areas) with increased likelihood of harm, disability and death. | - The necessary resources secured in the EASC IMTP/ Annual Plan - performance monitoring on a daily basis and month to date position - CASC Monthly quality and delivery meetings with WAST - Bi monthly CASC Quality and Delivery meeting with Welsh Government - CASC monthly Quality and Delivery Meeting with the Welsh Ambulance Services NHS Trust - Commissioner element of EMS Demand and Capacity plan for additional staff supported and implementation being monitored - Quality and Safety Report presented at every EASC meeting - Weekly dashboard shared across NHS Wales – sent to all EASC members and key senior NHS staff - Ambulance improvement plan developed, agreed and circulated weekly | - EASC IMTP accepted with accountability conditions awaiting outcome of WAST IMTP - Implementation of the commissioning intentions through the commissioning agreement - Role of the EASC Management Group to provide oversight on operational performance - Development of WAST performance improvement plan - Weekly dashboard of management information developed and shared across NHS Wales to capture progress - EASC Action plan includes detailed clinical review of amber incidents to understand clinical need of patients to assess improvement opportunities - Three key actions with appropriate indicators agreed with each HB during the winter period - Improvement plans are used by EASC Team, NHS Executive and WG for focus and consistent approach | •Ambulance Service Indicators - Daily weekly and monthly performance reports - Remedial Action plans (if required) - Specific targeted actions as required - Implementation of the Demand and Capacity Review - EASC Action Plan - CASC liaison with Chief Operating Officers (multiple arenas) | 5x4=20 | CXL 5x3= 15 |  | Aug-20 | Reviewed January 2024 Next review April 2024 Closely monitored, daily and weekly dashboard |
| 4508 | Chief Ambulance Services Commissioner | Set the Strategic Commissioning Direction | Failure by the whole system, policy makers, commissioners and providers to utilise EASC in matters which relate to its areas of responsibility during times of escalation | IF: The system does not utilise the arrangements in place at EASC Then: The governance and purpose of EASC will be undermined Resulting in: a lack of consistency, duplication of services and resources, poor governance and non compliance with the Statutory Instrument leading to unnecessary system pressures | - Accountable officers of health boards are members of EASC •Memorandum of understanding and commitment from all EASC members - Sharing information on service developments - Alignment to the 6 Goals for Urgent and Emergency Care Programme Board - Model Standing Orders agreed and reviewed annually - Commissioning Frameworks reviewed - ICAP health board and WAST commitment to meet monthly - National task and finish group on operational escalation and CASC an integral part | - Collaborative commissioning agreements - EASC Management group representing all organisations - Aligning EASC IMTP with WAST and Health board IMTPs - CASC meeting with Welsh Government planners - CASC IQPD meeting with Welsh Government - CASC Quality and Delivery meeting with WAST - Chair of EASC and CASC meetings with Health Boards - CASC Member of NHS Leadership Board | - Memorandum of understanding - Independent Chair Governance arrangements •Commitment to collaborative nature of working •External audit •Welsh Government and Commissioner support for EASC - EASC Action Plan - EASC Standing orders and Standing Financial Instructions | 4x2 =8 | CXL 4x1= 4 |  | Aug-20 | Reviewed October 2023 Next review April 2024 |

| Datix ID | Portfolio | Risk Domain (Strategic Objective) | Risk Title | Risk Description | Controls in place | Action Plan | Sources of Assurance | Rating (current) | Rating (Target) | Trend | Opened | Review date |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5005 | Chief Ambulance Services Commissioner | Effective Commissioning | Failure to take appropriate commissioning actions to support the provider in their management of patient safety and to minimise clinical risk during times of escalation | IF: Commissioning actions are not taken to manage patient safety and minimise clinical risks Then: Patients are more likely to come to harm Resulting in: poorer patient outcomes and patient experience, increased SAIs, litigation and reputational damage | - Discussion at EASC Committee - Discussion at EASC Management Group - CASC and WAST Quality & Delivery meeting - Sought clarification from WAST re Equality Impact Assessment - Agree red lines for handover delays to improve ambulance availability - Securing of funding for additional emergency ambulance capacity - Quality and Safety Report received at every EASC meeting - ICAP meeting overseeing performance and outcomes - Update to host Quality and Safety Meeting (23 January 2024) - Key item on EASC agenda - New Quality and Safety Report | - Joint escalation plan developed and approved at NHS Leadership Board now led by the NHS Executive - Provide necessary funding to WAST - Agreed with WAST 5 key actions for the winter period | - WAST Equality Impact Assessment (to be completed) •Commitment to collaborative nature of working and implementation of system-wide escalation policy - Ongoing discussions around system-wide escalation | 5X4 =20 | CXL 5X1 = 5 |  | Dec-21 | Reviewed January 2024 Next review April 2024 |
| 5370 | Chief Ambulance Services Commissioner | Effective Commissioning | Failure to secure sufficient ambulance capacity to meet the needs of the population | IF: sufficient ambulance capacity is not available Then: organisational and clinical safety levels of escalation will be higher and for longer durations within the clinical safety plan and patients will not receive a response Resulting in: increasing number of patients not receiving an ambulance response which is an unsatisfactory service for the people of Wales (or within specific health board areas) with increased likelihood of harm, disability and death. Lack of compliance with statutory requirements for EASC. | - The necessary resources secured in the EASC IMTP performance monitoring on a daily basis and month to date position - Bi monthly CASC IQPD meetings with Welsh Government - CASC monthly Quality and Delivery Meeting with the Welsh Ambulance Services NHS Trust - Commissioner element of EMS Demand and Capacity plan for additional staff supported – implementation being monitored - Quality and Safety Report presented at every EASC meeting - New demand and capacity review commissioned - ICAP meetings with health boards and WAST - Performance dashboard - IMTP tracker - Key item on EASC agenda - New Quality and Safety Report - Ambulance improvement plan developed, agreed and circulated weekly | - Delivery of EASC IMTP and WAST IMTP - Implementation of the commissioning intentions through the commissioning agreement - Role of the EASC Management Group to provide oversight on quality and safety - Development of WAST performance improvement plan - EASC Action Plan includes detailed clinical review of red incident to understand clinical need of patients to assess improvement opportunities - Actions from the Ministerial summit on handover improvement - Integrated Commissioning Action Plan (ICAP) work - Agreed with WAST 5 key actions for the winter period - Three key actions with appropriate indicators agreed with each HB during the winter period - Improvement plans are used by EASC Team, NHS Executive and WG for focus and consistent approach | •Ambulance Service Indicators - Daily weekly and monthly performance reports - EASC Action Plan - CASC liaison with Chief Operating Officers - EASC receive a quality and safety report at each meeting - New D&C for EMS (starting summer 2023) - ICAPS | 5x5=25 | CXL 5x2= 10 | New | Jan 23 | Reviewed January 2024 Next review April 2024 Review position when red and amber performance improve dramatically |