## NEPTS
Appendix 2 2019/20 Quarter 3 NEPTS Framework Improvements and Performance Improvements
Reference | CAREMORE™ | 5 Step Model | Summary | Full Description | Lead | Timescale | NCCU Status | WAST Status Q2 | Q1 & Q2 updates | WAST Status Q3 | Q3 updates | Q4 updates
Table 1A | Activities | Across the steps | Data repository | Data repository aligned to report activity against relevant step | Nicola Bowen - NEPTS Head of Transformation | <12 Months | ongoing | Ongoing on target | Undertaking a review of progress to date | Improved | Qliksense developed and in final test stages
Table 1A | Activities | Step 1 | Activity Step 1 | Step 1 - Ensure NEPTS specific engagement activity can be identified | Nicola Bowen - NEPTS Head of Transformation | <6 Months | improved | Some Attention Required | Current activity defined. Transport Solutions proposal will aid this | On-going | Proposal developed by PECI team and listed for DAG Jan 2020
Table 1A | Activities | Step 4,Step 5 | Activity Step 4&5 | Step 4/5 – ensure activity is clearly described within the relevant step | Nicola Bowen - NEPTS Head of Transformation | <3 Months | ongoing | Ongoing on target | Ongoing work. | On-going | Work in progress
Table 1A | Resource Envelope | Across the steps | Expenditure by HB across 5 steps | Develop infrastructure to be able identify how much is spend at a HB level across the 5 steps | James Haley - Finance Business Partner | >12 Months | ongoing | Ongoing on target | Local Measures in place to monitor this alongside transfer of work. To date only 4 HB left to transfer: AB, CTMUHB & PTUHB BCU. Development work on transferred HB's is underway & ongoing | On-going | Update as at Q1/Q2
Table 1A | Resource Envelope | Across the steps | 2018/19 Financial Assumptions and Plan vs 2019/20 | Review of 2018/19 IMTP financial assumptions and financial plan versus forecast outturn for 2018/19 and 2019/20 financial assumptions and financial plan | James Haley - Finance Business Partner | <3 Months | ongoing | Ongoing on target | Review of financial plan in progress | Complete | Complete
Table 1A | Resource Envelope | Across the steps | Financial value payable by EASC | Financial Value Payable by EASC and associated assumptions. | James Haley - Finance Business Partner | <3 Months | completed | Ongoing on target | Ongoing review, forms part of EASC discussions Currently still funded by HB's | Complete | Update as at Q1/Q2
Table 1A | Model of Care | Across the steps | Wiring diagram | Model of Care wiring diagram updated following implementation of plurality model. | Nicola Bowen - NEPTS Head of Transformation | >12 Months | Unknown | Ongoing on target | A new wiring diagram is in development to illustrate the positive changes & Improvements post-transfer for Hywel Dda. | On-going | Update as at Q1/Q2
Table 1A | Operational Arrangements | Across the steps | 02 Schedule | Update O2 Schedule – Application of the Model of Care following enactment of plurality model for each HB | Nicola Bowen - NEPTS Head of Transformation | >12 Months | improved | Ongoing on target | Last update of 02 schedules completed June 2019.4 Health Boards yet to submit, although work in progress - AB, CTMUHB & PTUHB BCU | On-going | Update as at Q1/Q2
Table 1A | Operational Arrangements | Across the steps | 03 Schedule | Update O3 Schedule – extant policies, protocols & pathways following enactment of plurality model for each HB | Nicola Bowen - NEPTS Head of Transformation | >12 Months | Unknown | Some Attention Required | Outstanding until the development of the national model - in progress | On-going | Update as at Q1/Q2
Table 1A | Operational Arrangements | Across the steps | Operational Arrangements | Operational arrangements to be reviewed by EASC on an ongoing basis. | James Rodaway - NCCU Head of Commissioning & Programming | In Place | completed | Complete | Operational Groups set up, NEPTS DAG and Management Group | Complete
Table 1A | Operational Arrangements | Across the steps | 2019-22 IMTP Actions | Inclusion of completed IMTP 2019/20 tables following EASC IMTP approval | Mark Harris - Interim Deputy Director | >12 Months | ongoing |  | Work in progress - summaries to be provide to HB's to help shape HB's IMTP Project Proposals | Complete | IMTP 20/21 in development in line with NHS timelines
Table 1A | Operational Arrangements | Across the steps | Commissioning Templates | NEPTS QDF to be signed December 2018. | TBC - Planning & Performance | <3 Months | completed | Complete | NEPTS QDF produced, with WAST for signing | Complete
Table 1A | Operational Arrangements | Step 3,Step 4,Step 5 | Provider Framework | To record and manage the framework of providers used to deliver the NEPTS plurality model. | Nicola Bowen - NEPTS Head of Transformation | >12 Months | ongoing | Ongoing on target | Lyndon Powell undertaking work to provide robust Framework for all providers. Implementing a Dynamic Purchasing System through 365 will support this | On-going | Update as at Q1/Q2
Table 1A | Review of Performance | Across the steps | R2 Schedule | Develop Schedule R2: Data repository covering A1 Activity, RE1 Resource Envelope, R1 Performance; enabling self-assessment against the Core Requirements of Care Standards; plus local measures by organisations. | Nicola Bowen - NEPTS Head of Transformation | <12 Months | ongoing | Ongoing on target | Internal work being undertaken in WAST to develop further via Qliksense but will be managed as part of the QDF | On-going | Update as at Q1/Q2
Table 1A | Review of Performance | Across the steps | Data Repository | Maintain data repository covering A1 Activity, RE1 Resource Envelope, R1 Performance Measures | Nicola Bowen - NEPTS Head of Transformation | <12 Months | ongoing | Ongoing on target | Internal work being undertaken in WAST to develop further but will be managed as part of the QDF | On-going | Update as at Q1/Q2
Table 1A | Review of Performance | Across the steps | Self Assessment of Care Standards | WAST undertake self-assessment related to the Core Requirements in Care Standards | Nicola Bowen - NEPTS Head of Transformation | <6 Months | Unknown |  | Position unknown | On-going | Plan required for self-assessment against the care standards |  | 1 improved
Table 1A | Evaluation | Across the steps | Baseline Data | Recording of baseline data for all NEPTS activity& resources for each HB. | Nicola Bowen - NEPTS Head of Transformation | In Place | ongoing | Ongoing on target | Work in progress as part of the Transfer of Work. 4 Health Boards to transfer across | On-going | Update as at Q1/Q2 |  | 5 complete
Table 1A | Evaluation | Across the steps | Role of PDEG | Evaluation programme for NEPTS overseen by PDEG | Hugh Bennett - Assistant Director Commissioning & Performance | <12 Months | Unknown |  | Position unknown - work outstanding. | Deterioration | No evaluation programme agreed between NCCU/WAST. |  | 6 | 11 | 2 | 19
Table 1A | Evaluation | Across the steps | Evaluation Programme | Creation of evaluation methods and programme of work. | James Rodaway - NCCU Head of Commissioning & Programming | <6 Months | Unknown |  | Position unknown - work outstanding | Deterioration | Approach not agreed between NCCU/WAST. |  |  |  |  | 19
Table 1B | Care Standards | Step 1 | Care Standards | Compliance with care standards for previously extant Health Board/WHSSC/Velindre services | Nicola Bowen - NEPTS Head of Transformation | >12 Months | Unknown |  | Position unknown | Deterioration | Plan required for self-assessment against the care standards
Table 1B | Resource Envelope | Across the steps | Review of Business Case | Development of a fully costed business case to meet the Cabinet Secretary expectations from the 2015 business case. | Mark Harris - Interim Deputy Director | <3 Months | ongoing | Ongoing on target | Transport Solutions proposals agreed | On-going | Update as at Q1/Q2
Table 1B | Resource Envelope | Across the steps | WAST Resources | Demonstrate WAST NEPTS resources are being utilised effectively following transfer of HBs. | James Haley - Finance Business Partner | >12 Months | ongoing | Ongoing on target | Transfer of Work providing greater clarity and quality of data (includes in and out of scope). To date only 4 HB left to transfer: AB, CTMUHB & PTUHB BCU | On-going | Local measures will help this
Table 1B | Operational Arrangements | Across the steps | Quality Assurance | WAST to ensure robust quality assurance to manage providers required to deliver the plurality model | Nicola Bowen - NEPTS Head of Transformation | >12 Months | ongoing | Ongoing on target | Lyndon Powell undertaking work to provide robust QA Framework with all providers | On-going | Update as at Q1/Q2
Table 1B | Operational Arrangements | Across the steps | Internal Audit recommendations | Implement improvements identified within the Internal Audit of NEPTS provision November 2018. | Mark Harris - Interim Deputy Director | <12 Months | improved | Ongoing on target | improvements being delivered consistently | On-going | Dec 19 follow up audit commenced.
Table 1B | Review of Performance | Across the steps | Core requirements | Compliance with core requirements of care standards reported on a six monthly basis. | Nicola Bowen - NEPTS Head of Transformation | <12 Months | Unknown |  | Position unknown | On-going | Assessment will be undertaken in Q4.
Table 1B | Review of Performance | Across the steps | Improvement in Activity Performance | WAST to demonstrate how activity performance is improved in each HB following enactment of the plurality model. | Nicola Bowen - NEPTS Head of Transformation | >12 Months | ongoing | Ongoing on target | In progress - will be completed once Transfer of Work undertaken - 4 Health Boards left to transfer (AB, CTMUHB & PTUHB) BCU | On-going | Update as at Q1/Q2
Table 1B | Review of Performance | Across the steps | Improvement in Efficiencies | WAST to demonstrate savings and efficiencies in each HB following enactment of the plurality model | James Haley - Finance Business Partner | >12 Months | ongoing | Ongoing on target | In progress - will be completed once Transfer of Work undertaken - 4 Health Boards left to transfer (AB, CTMUHB & PTUHB) BCU | On-going | Update as at Q1/Q2
Table 1B | Review of Performance | Across the steps | Staff Experience | Report & consider improvements following measuring staff experience | Mark Harris - Interim Deputy Director | <12 Months | ongoing | Ongoing on target | Work in progress | On-going | Work to do to develop on-going service specific feedback channels with staff over & above NHS survey |  |  | 9 | 1
Table 1B | Review of Performance | Across the steps | Patient Experience | Report & consider improvements following measuring patient experience. | Mark Harris - Interim Deputy Director | <12 Months | ongoing | Ongoing on target | Work in progress | On-going | Links to PECI proposal above |  |  |  |  | 10

## Sheet1 (hidden)
Urgent Attention Required
Some Attention Required
Ongoing on target
Complete
Closed