[image: image1.jpg]Pwyllgor Gwasanaethau
Ambiwlans Brys
Emergency Ambulance
Services Committee











Agenda Item 1.5.1
Action Log 

JOINT COMMITTEE MEETING

Update for meeting on 30 January 2024
	Minute
	ACTIONS
	Lead
	Progress

	December 2023

	EASC 23/129
	Performance Report

Members to confirm a minimum of two priority actions from ICAPs to the CASC
	HBs and WAST
	Perf Report

	
	Members to work with the CASC to identify issues and provide assurance that actions have been implemented consistently within the system (e.g. SDEC, Clinical Advice Hubs immediate diagnostic front door pathways etc) in order to mitigate any unacceptable patient safety risks.

Members agreed to provide responses in relation to local plans and commitment by the first week of January 2024 to the CASC for ongoing coordination and embedding into ongoing processes, this would be a blended approach across HBs and WAST.
	ALL
	Agenda item

CASC Report

	EASC
23/130
	Quality and Safety Report

EASCT to support the work in Hywel Dda for wider system learning
	EASCT
	Contact made with HDda

	EASC

23/131
	Commissioning Update 

EASC Team to consider comments received on the Commissioning Intentions from members of the EASC Management Group and NEPTS/EMRTS Delivery Assurance Groups
	EASCT
	Agenda item

Commissioning update report

	
	EASC Team to discuss Commissioning Intentions with WAST and EMRTS colleagues


	EASCT
	Discussions held with WAST and EMRTS

	EASC

23/132
	EMRTS Service Review
Commissioner to send a formal response to Llais on behalf of the Committee confirming the agreed EASC position and clarifying the adjusted timeline for the Review
	EASCT
	Agenda item

EMRTS Service Review report

	
	Issue a public communication confirming the Committee’s agreed position and next steps for the EMRTS Service Review including any adjusted timeline
	EASCT
	

	
	Make operational arrangements to deliver the EASC agreed next steps of the process
	EASCT
	

	EASC

23/133
	CASC Report

Members to provide comments on WAST Stakeholder Briefing to the CASC in order to prepare a response on behalf of the Committee.  Draft to be shared with health boards for comment.
Once responses are received on the recent WAST briefing, before, at the meeting or following a response would be sent. This would be shared in advance with Members

	
	TBC

	
	Commissioners had an opportunity to input actions for the Winter Ambulance Improvement Plan and these would be forwarded to Welsh Government as soon as possible.
	
	Complete – CASC Report 

	November 2023

	EASC 23/111
	Performance Report 
Monitor access to same day emergency care services; collaborative work between WAST and ED staff including access to diagnostics; focus on the role of the clinical hubs and progress opportunities; focus efforts on 4 hour red lines. Provide regular updates on a site by site basis and regional basis
	EASC T

WAST

HBs
	Agenda item

Performance report

	
	Response to the increase in red calls related to ‘breathing difficulties’ consider developing a respiratory plan
	CASC
	To be added to EASC team workplan 24/25

	
	Progress discussions with the Primary Care and the Six Goals for Urgent and Emergency Care National Programmes regarding virtual wards for acute respiratory illness / infection
	CASC
	To be added to EASC team workplan 24/25

	
	Review the work undertaken in England that identified an over-triage rate in relation to respiratory and the opportunity to include conversion to conveyance and admission rates in relation to respiratory red calls
	CASC
	To be added to EASC team workplan 24/25

	
	Consider alternatives to the medical model at the front door, a nurse/therapy model was suggested
	CASC
	To be added to EASC team workplan 24/25

	
	Note to be sent to capture points above following the meeting - include the areas for specific focus over the coming months, monitoring and reporting arrangements, the escalation process and use of the ICAP process to coordinate these efforts
	CASC
	Superseded by priority action from ICAPs 

	EASC 

23/112
	Quality and Safety Report

Review of Remote Clinical Services – update on work to implement recommendations to be presented following EASC Management Group
	EASCT
	January 2024

	
	Work between WAST and HB colleagues to understand the level of harm within the system and to develop additional processes to assure the Committee
	WAST / HBs
	Early 2024

	
	Work together in order to consider prevention of future death notices received from the HM Coroner and the different approaches of different HM Coroners, this required an all-Wales review and including HM Coroners themselves.
	EASC T

HBs
	To be added to EASC team workplan 24/25

	EASC 23/113
	EMRTS Service Review
Health boards agreed to nominate staff to undertake the assessment of the options
	HBs
	EMRTS Report

	EASC 23/115
	Transfer Discharge and Repatriation
A Task and Finish Group would be developed to further this work
	CASC
	Initial work undertaken – next steps to be added to EASC team workplan 23/25

	Sept 2023

	EASC

23/089
	Performance Report Integrated Commissioning Action Plans (ICAP) and developing the trajectory of improvements to share with members and Welsh Government
	EASC Team / WAST
	Completed

	
	Additional 100 WTE staff and the improvements in health board areas and its impact including capacity and constraints to be added in the next provider report
	WAST
	Superseded Winter Ambulance Improvement Plan 

	July 2023

	EASC 23/070
	Learning from the North East Ambulance Service review and the potential to undertake a gap analysis to secure any insight or learning 
	EASC Team
	Completed – Dec 23 EASC

	
	Develop a longer-term strategy for NEPTS following the completion of the business case and adapting to the ongoing changes within the service. The final report would be presented at a future meeting 
	EASC Team
	Agenda item

Commissioning update report 

	EASC 23/073
	Red Release information - Work to develop confidence in the information included the health board Chief Operating Officers and their teams who receive the unvalidated report and therefore can challenge the data with respect to their areas. Further updates will be provided as the work progresses – through EASC Management Group
	EASC Team
	Agenda item

Commissioning update report 

	EASC 23/074
	Health Education and Improvement Wales (HEIW) – Agreed that Alex Howells, CEO of HEIW would be invited to periodically attend the Committee meeting.

	Ctte Sec
	Forward look March 2024
Legacy for New JCC??

	May 2023

	EASC 23/049
	Performance Report

Opportunity to use SPC (Statistical Process Control) charts to help understand variation and guide to taking the most appropriate action – to be shared with members on request
	EASC Team
	Performance Report
Complete/closed

	March 2023

	EASC 23/028
	Performance Report – Workshop to link data and system learning to improve performance
CASC to lead a workshop to learn from across the system to improve performance
	CASC
	Agenda item
CASC Report

	July 2022

	EASC 22/79 &
EASC 23/046
	Different staff input to WAST Control / call options

Potential to consider social care, care homes and maternity (included in WAST IMTP planning)
	WAST
	Impact to be evaluated.  
Item to remain on action log

Legacy items

	May 2021

	EASC 21/26
	Committee Effectiveness

Discussion re wider membership with patient voice or additional independent members
	Chair


	Ongoing 
To remain on action log

Legacy items


CASC

	Action Log 


	Page 4 of 3
	Emergency Ambulance Services Committee Meeting
30 January 2024



