## Slide 1
Emergency Ambulance Services Committee
IMTP Tracker
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK

## Slide 2
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
Introduction
  The 2023-26 EASC IMTP set out a number of performance improvement ambitions and performance enablers for Emergency Ambulance Services
  This slide deck sets out the progress to date against each of the commitments.
EASC IMTP 23/26 Tracker

## Slide 3
Summary – Performance Improvement
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker

## Slide 4
“Cant Sends” - Reduced by 75-95% over 2023/24
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
The level of cant sends have remained significantly lower in each month this year compared to last.
However, each incident is a patient that did not get a response, further work is required to minimise these incidents.
*CSP Can’t sends only
Chart: 
| April | May | June | July | Aug | Sep | Oct | Nov | Dec
2022 | 670 | 161 | 611 | 683 | 358 | 348 | 852 | 372 | 2652
2023 | 46 | 61 | 57 | 154 | 208 | 628 | 200 | 164 | 793

## Slide 5
Red Performance – 60% by end of Q1
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
EASC committed to achieve 65% by end of Q2 with sustained incremental improvement in Q3/4
Further substantial improvements to system flow and ambulance availability are required to address this commitment.
Chart: 
| April | May | June | July | August | September | October | November | December
 | 0.53 | 0.54 | 0.55 | 0.526 | 0.505 | 0.487 | 0.472 | 0.495 | 0.489

## Slide 6
Longest Red – 95th Percentile 30 min by end of Q1
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
Chart: 
Apr | 0.015938
May | 0.014965
Jun | 0.015405
Jul | 0.017176
Aug | 0.016377
Sep | 0.016875
Oct | 0.016377
Nov | 0.015868
Dec | 0.017269
Initial improvements from Q1 have not been sustained.
In July 2023 EASC agreed to update their Q2 ambition– to be less than 18 min
Further substantial improvements to system flow and ambulance availability are required to address this commitment.

## Slide 7
Amber Median - < 90 min by end of Q1
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
EASC committed to achieve 45 min by end of Q2 with less than 30 min by the end of 2023/24.
Further substantial improvements to system flow and ambulance availability are required to address this commitment.
Chart: 
Apr | 0.04412
May | 0.040394
Jun | 0.042431
Jul | 0.049421
Aug | 0.055984
Sep | 0.058264
Oct | 0.061956
Nov | 0.050995
Dec | 0.070764

## Slide 8
Longest Amber – 95th Percentile 8 hours by end Q1
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
At the July 2023 meeting, EASC agreed to revise the improvement ambitions to Quarter 2 less than 4.5 hours and Quarter 3 less than 3.5 hours with sustained incremental improvement by in Q4
Further substantial improvements to system flow and ambulance availability are required to address this commitment
Chart: 
Apr | 0.2323
May | 0.20976
Jun | 0.20294
Jul | 0.25315
Aug | 0.30861
Sep | 0.35824
Oct | 0.33438
Nov | 0.25741
Dec | 0.39068

## Slide 9
Handover Hours – 15,000 Lost per month by end of Q2
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
EASC committed to achieve 12,000 hours per month by end of Q3 with sustained and incremental improvement in Q4
Further substantial improvements to system flow and ambulance availability are required to address this commitment
Chart: 
Apr | 22990.3639
May | 20440.6122
Jun | 18548
Jul | 19119
Aug | 19060
Sep | 19610
Oct | 23222
Nov | 20126
Dec | 22769

## Slide 10
Longest Handover – No Handover >4 Hours in 2023/24
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
Requirement for all sites to eradicate waits over 1 hour by end of April 2025
Further substantial improvements to system flow are required to address this commitment
Chart: 
Apr | 2030
May | 1625
Jun | 1440
Jul | 1452
Aug | 1475
Sep | 1528
Oct | 1889
Nov | 1680
Dec | 2008

## Slide 11
Longest Handover – No Handover >1 Hours by April 2025
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
Requirement for all sites to eradicate waits over 1 hour by end of April 2025
Welsh Government requested HB forecast to end of March 2024.
Further substantial improvements to system flow are required to return to the trajectory
Chart: 
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Trajectory | 6519 | 5687 | 4975 | 5039 | 4665 | 4476 | 4505 | 4380 | 4560 | 4744 | 4156 | 4317
Actual | 6116 | 5808 | 5308 | 5724 | 5674 | 5708 | 6449 | 5816 | 6044

## Slide 12
Summary – Performance Enablers – WAST
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
Progress
Units of hours produced (UHP) has averaged 92.6% between April and December 2023, with a range of 86.5% - 96.8%
Sickness absence was 8.79% in November
Hear and Treat has averaged 11% between April and December 2023
Clinical assessment of red calls in place

## Slide 13
Summary – Performance Enablers – Six Goals
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
Progress
Urgent Primary Care - Work ongoing to understand referral rates
Same Day Emergency Care (SDEC) – Limited progress in increasing SDEC direct access activity.
111- Work ongoing to understand how abandonment rates impact 999
Connected Support Cymru – extended to end of 2023/24

## Slide 14
Summary – Performance Enablers – Targeted
HTTPS://EASC.NHS.WALES
CTM_CASC_EASC@WALES.NHS.UK
EASC IMTP 23/26 Tracker
Progress
Review of clinical desk completed by EASC, recommendations delivery plan being developed.