[image: image1.jpg]Pwyllgor Gwasanaethau
Ambiwlans Brys
Emergency Ambulance
Services Committee












Agenda Item 1.5.1
Action Log 

JOINT COMMITTEE MEETING 

Update for meeting on 23 July 2019
	Minute
	Action
	Lead
	Progress

	EASC 16/43

& EASC 18/05 & EASC 19/21
	Sub Groups 

Update summary on the role, function and membership of the sub groups as well as the progress on the work with WAST on the Clinical Governance Plan.
	CASC
	Agenda item 2.2 

CASC Update Report


	EASC 17/44 & 

EASC 17/73
&
EASC 19/21
	Emergency Medical Retrieval and Transfer Service (EMRTS) Gateway review
Further update on the direction of travel in relation to the recommendations of the gateway review to be provided
	CASC
	Agenda item 2.2

CASC Update Report 

	EASC 18/06

&

EASC 18/65

& 

EASC 19/21
	Integrated Performance Dashboard

To develop bespoke Health Board reports that will provide more HB specific data.  
	CASC & WAST
	Oral update
July 2019

	EASC 18/46 &

EASC 18/65
	Clinical Risk Review

The CASC confirmed an update on progress relating to this work between EAS Team and WAST Officers, will be presented to the September 2018 meeting of the Committee.  
	Clinical Director

NCCU
	Agenda item 3.2 

Clinical Risk Review Closure Report


	EASC18/107 &
EASC 19/21
	Expansion of EMRTS (Emergency Medical Retrieval and Transfer Service) – business case to include funding options – included in IMTP 
Business case to be received by EASC
	CASC

Dir NCCU
	Agenda item 2.2

CASC Update Report

	EASC 19/08 & 

EASC 19/21
	Mental Health Staff and the Clinical Desk

Conversation to be held with Chief Constable Gwent Police
	Judith Paget 
	Oral update

	
	Hold local workshops with Health Boards
Staff to be nominated to attend
	Dir NCCU

ALL
	Oral update

	
	CASC to raise the matter with the Director General at the Welsh Government for the potential to work across all 999 services
	CASC
	Oral update

	
	Report / position statement to be developed to capture the effective areas of work
	CASC
	Oral update

	EASC 19/08 & 

EASC 19/21
&

EASC 19/23
	Emergency Medical Retrieval Service (EMRTS) 

Refresh of the commissioning framework
	Dir NCCS
	To be confirmed
Was July 2019

	
	Cross Border and Regional Activity

CASC to provide additional information to Powys
	CASC
	Oral update

	
	‘A Healthier Wales’ Commissioning allocation

Report to be submitted to the next meeting on potential utilisation of the allocation
	CASC/Dir NCCU
	Agenda item 2.3

	EASC 19/12
	EASC Risk Register

Review of Risks and actions
	CASC
	Development Session

	EASC 19/23
	Chair

WAST CEO agreed to thank the WAST staff who hosted a recent visit by the Chair
	Jason Killens
	Oral update

	
	Chair’s objectives to be shared with the Committee Members
	CASC
	Completed

	EASC 19/26
	Nominated Deputies
Awaiting confirmation from Cardiff and Vale UHB
	CASC
	Oral update

	EASC 19/38
	Falls Schemes

Further evaluation to take place
	CASC
	September 2019

	EASC 19/41
	Red Performance

Quality Assurance process to be clarified and letter sent; discussion in relation to the use of advanced paramedic practitioners across Wales and key themes to be identified
	CASC
	Agenda item 2.2

CASC Update Report

	EASC 19/42
	Ambulance Quality Indicators

More detailed trend analysis would be undertaken on quality, performance and activity
	Dir NCCU
	Oral update

	EASC 19/44
	EASC Governance

Annual Governance Statement to be received at the next meeting for endorsement following Chair’s action to approve
	Board Secretary
	Agenda item 3.1


CASC
	Action Log 


	Page 2 of 2
	Emergency Ambulance Services Committee 

23 July 2019



