[image: image1.jpg]Pwyllgor Gwasanaethau
Ambiwlans Brys
Emergency Ambulance
Services Committee












Agenda Item 1.5.1
Action Log 

JOINT COMMITTEE MEETING
Update for meeting on 10 March 2020
	Minute
	Action
	Lead
	Progress

	EASC 17/44 & 

EASC 17/73
& EASC 19/21

& EASC 19/76
	Emergency Medical Retrieval and Transfer Service (EMRTS) Gateway review
Further update on the direction of travel in relation to the recommendations of the gateway review to be provided
	Stephen Harrhy
	Agenda item 
CASC Report

	EASC 18/06

& EASC 18/65

& EASC 19/21

& EASC 19/92
	Performance Dashboard

To develop bespoke Health Board reports that will provide more HB specific data.  
	Ross Whitehead
	Agenda item
Performance Dashboard

	EASC 19/08 & 

EASC 19/21
& EASC 19/23

& EASC 19/92
	Emergency Medical Retrieval Service (EMRTS) 

Refresh of the commissioning framework
	Julian Baker
	Agenda item
CASC Report 

	EASC 19/12
	EASC Risk Register

Review of Risks and actions
	James Rodaway
	Agenda item

Governance Report

	EASC 19/55

& EASC 19/92
	Mental Health

Additional information to be developed and shared to assist Members with the work to date
	Shane Mills

/ Lead CEO
	Agenda item
CASC Report

	EASC 19/75
	Chair and CASC Meetings

Invites to meet with all health boards and NHS Trust meetings
	Members
	To confirm once all completed

	EASC 19/77
	WAST Staff Pipeline

Discussion with the provider about the relatively high number of re-sits
	Jason Killens
	Completed

	
	Handover Delays

WAST to develop an action plan for urgent agreement with HBs

· Procuring services from 3rd sector / or provide more unscheduled care staff

· Review the skill mix within the control 

· Support emergency departments by making staff available

	Jason Killens
	Completed

	
	RED improvement plan

To be developed and shared with Health Boards
	Jason Killens
	Completed 

	
	RED Performance requirements

Following the Management Group meeting health boards to be notified of requirements
	Stephen Harrhy
	Completed

	
	Good SAM app

Additional information to be shared to seek assistance from staff across NHS Wales
	Jason Killens
	Completed 

	EASC 19/78
	Reference Document on the  WAST Relief Gap Emergency Ambulance Service 

· Receive a plan outlining how WAST would return to 2013/14% levels of spending on frontline staff and recurrently resourced
· Use WAST contingency and 1% ‘A Healthier Wales’ funding slippage as non–recurrent allocation; money to be allocated on spend and with agreement on impact on performance 

· Receive a review what has happened to the funding provided to date 

· Tapering funding to be discussed as part of the IMTP process and linked to outcome of Demand and Capacity Review

· Handover improvement plan to be agreed by EASC
	Jason Killens

Stuart Davies
Stuart Davies
Stephen Harrhy
Jason Killens
	To be confirmed
Finance Report

Finance Report

EASC IMTP

To be confirmed

	EASC 19/79
	WAST Service Transformation

· Share the three service transformation initiatives suitable for national scale up with the Minister at the Chairs meeting with the Minister at the end of September 
	Jason Killens
	To be confirmed

	EASC 19/82
	Regional Escalation

· Ensure all organisation provide their escalation plans by 20 September 2019

· Individual site escalation plans

· Individual site full capacity plans

· The list of individuals that will undertake the national escalation calls this winter on behalf of each organisation. 

· Establish of task and finish group (aimed at assistant Chief Operating Officers) to provide a peer review process for the above plans, and finalise the proposals for enhancing the national escalation calls.

· Develop a bespoke training course for representatives on the call based on the Exercise Wales Gold course, with a specific focus on managing health services during periods of escalation. 

· Agreed that the revised process to be live by the 1 December 2019. 
	Members

Stephen Harrhy
WAST

All


	Completed
Completed
Completed
Completed 

	EASC 19/95
	ORH Demand and Capacity Review
· Receive the final version of the report at the next meeting.
	Stephen Harrhy & Jason Killens
	Completed

	EASC 19/97
	Serious Adverse incidents (SAI) 
· Additional information was requested in terms of the common themes of the SAIs (in more detail than handover delays) which would be reported to the Welsh Government
	Jason Killens
	To be confirmed


	EASC 19/97
	Red call and triage categorisation

Members felt it was important to better understand the reasons, Rachel Marsh agreed to provide further information from a deep dive as soon as possible
	Rachel Marsh
	Completed


	EASC 19/99
	Regional Escalation

The safe cohorting of patients was discussed at length, it was agreed that this should be discussed at the Chief Operating Officers meeting along with proposals for changing regional escalation arrangements
	CASC
	Completed


	EASC 19/100
	Developing the National Emergency Department Quality and Delivery Framework (EDQDF)

Receive a further update on progress during the summer of 2020
	Julian Baker
	Added to Forward Look

	EASC 19/103
	Governance
· EASC Standing Orders to be adopted by each Health Board
· Standing Financial Instructions to be presented when finalised
· Risk Register to be redeveloped in line with discussion meeting
	All

Stuart Davies

James Rodaway
	Completed
 To be confirmed

Agenda item Governance Report


	EASC 19/104
	EASC Commissioning intentions and IMTP

The Chief Ambulance Services Commissioner write to the Chief Executive at WAST as soon as possible clarifying the commissioning intentions of EASC for the next year.
	CASC
	Completed

	EASC 20/10
	Letter of support for the WAST IMTP
Letter to be shared with Members as soon as possible – sent on 31 Jan 2020
	CASC
	Completed

	EASC 20/11
	Forward Plan of Business
Annual Reports to be received from all sub groups 
	Sub Group leads
	To be confirmed

	EASC 20/12
	Chief Ambulance Services Commissioner’s Report

Share terms of reference for Ministerial Ambulance Availability Task Force as soon as possible
	CASC
	To be confirmed

	
	Emergency Medical Retrieval and Transfer Service

Chair and CASC to meet with Air Ambulance Charity and report back
	Chair & CASC
	To be confirmed

	
	Research related to triage tools 

Research information related to breathing problems – card 6 to be shared with EASC Management Group
	Jason Killens
	To be confirmed

	EASC 20/15
	Finance Report

A Healthier Wales allocation to be quantified by the end of February
	Stuart Davies
	To be confirmed

	EASC 20/16
	EASC Governance Update

The risk register to be reviewed in line with the host body arrangements and progress to be presented to the next meeting
	James Rodaway & Gwenan Roberts
	Agenda item Governance Report

	
	Annual Reports for the Committee and all sub groups

Agreed to receive an annual report to assist to evaluate the effectiveness of the Committee; receive reports from all sub groups
	Gwenan Roberts

Sub Group leads
	To be confirmed




CASC
	Action Log 


	Page 4 of 4
	Emergency Ambulance Services Committee 

10 March 2020



