AGENDA ITEM

2.2

EMERGENCY AMBULANCE SERVICES COMMITTEE (EASC)

welsh ambulance services nhs trust (WAST) provider update

| Date of meeting | 15 March 2022 |
| --- | --- |

| FOI Status | Open/Public |
| --- | --- |

| If closed please indicate reason | Choose an item. |
| --- | --- |

| Prepared by | Rachel Marsh, Director of Strategy, Planning and Performance (WAST) |
| --- | --- |
| Presented by | Jason Killens, Chief Executive WAST |
| Approving Executive Sponsor | Chief Executive |

| Report purpose | FOR DISCUSSION / REVIEW |
| --- | --- |

| Engagement (internal/external) undertaken to date (including receipt/consideration at Committee/group) |  |  |
| --- | --- | --- |
| Committee/Group/Individuals | Date | Outcome |
| (Insert Name) | (DD/MM/YYYY) | Choose an item. |

| ACRONYMS |  |
| --- | --- |
| ABUHB CTMUHB D&C EMS NCCU NEPTS SAI WAST | Aneurin Bevan University Health Board Cwm Taf Morgannwg University Health Board Demand and Capacity Emergency medical services National Collaborative Commissioning Unit Non-emergency patient transport services Serious Adverse Incident Welsh Ambulance Services NHS Trust |

- SITUATION/BACKGROUND

  - The purpose of this report is to provide EASC with an update on key issues affecting quality and performance for EMS and NEPTS and to provide an update on commissioning and planning for EMS and NEPTS.

- SPECIFIC MATTERS FOR CONSIDERATION BY THIS MEETING (ASSESSMENT)

CoVID-19

2.1	WAST continues to track CoVID-19 and related metrics through its weekly CoVID-19 Intelligence Pack.  It is clear that the third wave has peaked and the trend is now downward (positive tests). WAST is currently at escalation level 3 (4 being the highest), but there is a continued need for WAST to use its highest level of Clinical Safety Plan, level 4, which means the use of clinical screening for Amber 1 patients and unable to send for Amber 2.  The reasons for this are complex, and not just CoVID-19 demand, and include high abstractions (linked directly to CoVID-19, but also workforce fatigue) and high system pressure, in particular, handover lost hours.

2.2	WAST now undertakes seasonal forecasting and modelling as a matter of routine. WAST collaborates with the EASC Team at the NCCU on this work via its Forecasting & Modelling Group, with the modelling results for winter being shared with senior stakeholders. The modelling indicated a very difficult winter period, with the results being used to help seek military aid.  WAST decided not to undertake further modelling using Omicron forecasts, but instead focus on quarter 1 2022/23 i.e. after military aid, which will cease on 31 Mar-22.  The modelled results (for Apr-22) have been made available to the CASC and his team. The modelled results indicate that WAST will need to operate the Clinical Safety Plan at level 4 in order to keep Red 8 minute performance above 60% and Amber 1 median under one hour.

2.3	As previously reported WAST stood up its pandemic structures (Pandemic Plan) during the third wave, which it is about to stand down, and introduced an organisation wide Performance Improvement Plan (PIP), which sets out the actions being taken to mitigate the risks highlighted in the modelling, including increasing capacity where possible (re-engaging with the military and fire & rescue services) and deployment when required of the Clinical Safety Plan.  The PIP is regularly reported on to the CASC and is being rolled forward into quarter 1 2022/23 due to the continued system pressures. WAST has written to the CASC requesting continued support for a number of mitigations that would require funding e.g. cohorting, continued use of St John Ambulance etc.

EASC is asked to NOTE that: the CoVID-19 third wave has peaked, WAST has de-escalated to level 3, WAST continues to have to operate its clinical safety plan at level 4 (maximum), WAST is receiving military aid, but this will end on 31 Mar-22; modelling for Apr-22 post military aid indicates that WAST will need to continue operating at the maximum level of clinical safety plan, WAST will continue to tactically performance manage delivery against an organisational wide PIP (which is also regularly reported to the CASC); and that WAST is seeking funding for the continuation of patient safety mitigation into quarter 1 2022/23.

Quality, Safety & Patient Experience

Patient Response Times in the Community

2.4	One of the key indicators which measures the quality of the service provided is the timeliness of the response by WAST to patients waiting in the community. The graphs below show the current response times performance for Red calls and for Amber One calls. Both graphs show that response times have continued to worsen throughout 2021.  Inevitably these worsening times have had an impact on patient safety.

2.5	The Red 8-minute target was not achieved in Jan-22. The percentage of emergency responses to Red incidents within 8 minutes was 53% (target 65%) with 95% of Red calls receiving a response within 22 minutes. Red 9 minute performance was 60% and Red 10 minute performance 65%.

2.6	At previously requested by EASC missed Red incidents by time of day is demonstrated in the following infographic by day and hour (Jan-22).

2.7	WAST reviews missed Red incidents as a matter of routine and is aware of the increase in missed Reds in the evening and early hours. WAST has undertaken modelling which has identified four demand hotspots.  Under more normal conditions WAST would target Rapid Response Vehicles (RRVs) at these times; however, due to CoVID-19 and the level of abstractions WAST is currently operating a tactical approach to ambulance production with a focus on Emergency Ambulances, which can convey patients and have a higher utilisation. WAST is currently re-rostering (see 2.43), which will see the withdrawal of the RRV as a planned ambulance resource and its replacement with the Cymru High Acuity Response Unit (CHARU) predicated on modelling to deliver the Red 8 minute target per health board and improve clinical outcomes through on scene improved clinical leadership.

2.8	The Amber One median percentile in Jan-22 was 57 minutes and the Amber 95th percentile was four hours 51 minutes.  The Amber 1 performance parameters used in the EMS Demand & Capacity Review were 35 minutes (Dec-21 position) and 18 minutes (Dec-24 position) respectively.

2.9	These very long Amber One median times mean that the patient waiting times in the “Amber tail” are a particular concern from a patient safety perspective (it is where the bulk of serious adverse incidents occur).  As part of its quality, safety and patient experience arrangements, WAST continues to monitor the longest patient responses. The table below shows the number of patients who had to wait 12 hours or over.  The table shows that very long waits were almost eliminated during the first wave, but subsequently returned as system pressures increased.  There were 503 long waits in Jan-22, a reduction when compared to Dec-21, but still very high.

2.10	These long response times impact on patient safety and outcomes. WAST has been supplying weekly information on quality, safety and patient experience to the CASC and monthly information through the CASC Assurance & Delivery meeting. This information includes more detailed analysis, patient stories (positive and negative) and patient feedback from surveys.

2.11	WAST supplies health boards with a monthly report on one hour and over patient waits.

2.12	In extreme cases, long response times can lead to National Reportable Incidents (NRIs). In the last 3 months, 71 patient safety incidents have been passed to health boards as part of the joint investigation framework (Appendix B).

2.13	Whilst there are many factors affecting response times, which are described later in this report, one of the factors outside WAST’s control is the number of ambulances which wait longer than 15 minutes to transfer patients into secondary care at Emergency Departments (EDs). The graph below shows the number of ambulance hours that are lost outside EDs which, if released earlier, would have reduced patient waits in the community. As with the other graphs, during the first wave of the pandemic, the number of lost hours decreased very significantly, but they are now higher than those seen in the worst of winter.

2.14	22,563 hours were lost to handover in Jan-21 (or 1,962 11.5 hour shifts of WAST’s actual conveying resource), compared to 8,416 in Jan-20, 13,056 in Dec-19 and 6,038 in Dec-18, the benchmark used in the 2019 EMS Demand & Capacity Review.  The 2021/22 EASC EMS commissioning intentions include: “NHS Wales is a significant outlier in the UK and Internationally for lost productivity due to extended notification to handover times. By the end of 2021/22 NHS Wales will have reduced 1 hour waits to less than 5% of total arrivals and ensured that total lost hours at Welsh Hospitals do not exceed 150 hours per day on 95% of the year”. The draft 2022/23 intentions include the development of improvement trajectories per site.

2.15	In the last three months WAST has reported 18 National Reportable Incidents (NRIs) to the Delivery Unit and continues to have regular dialogue with EASC through the NCCU.

2.16	The WAST has previously written (27 Jul-21) to the Director General detailing the clinical risk that WAST is carrying and the patient harm that is occurring in communities across Wales and more recently WAST has written to the CASC (24 Feb-22) on projected clinical risk into quarter 1 2022/23. WAST has reviewed and updated its Demand Management Plan, now known as the Clinical Safety Plan (CSP).

A health board escalation policy is currently in development nationally that connects with the WAST CSP and that there is a clear system wide approach to shared risk and patient safety.  WAST has supported this work by providing health boards with access to its modelling software.  This system wide approach to clinical safety is due to go live in Apr-22.

Health & Safety

2.17	There have been 1,491 reported staff positive CoVID-19 since the start of the pandemic (Mar-20 to Dec-21). 201 positive cases were reported in January-22.  All cases continue to be investigated and reviewed and, where applicable, reported to the Health and Safety Executive (HSE) in line with the Reporting of Injuries, Diseases and Dangerous Occurrences Regulations (RIDDOR) 2013.  61 RIDDORS have been submitted to the HSE for potential exposure to CoVID-19 to date.  There have been 548 CoVID-19 cases subject to more detailed investigation to ensure there is a high degree of certainty that the infection was acquired as part of the work undertaken by WAST staff before reporting the cases to the HSE.

2.18 The internal investigation into the serious road traffic collision in Apr-21 at Dolgellau is coming to its conclusion with the investigation report to finalised in Mar-22.

2.19 The “Pump Prime” phase of the Working Safely Programme continues with a full complement of staff in post in Jan-22.  The Working Safely Programme Board and the Working Safely Dynamic Delivery Group have completed the risk register for the programme setting out the risk relating to the delivery of the programme. This will help ensure suitable actions are in place to ensure the smooth introduction of the programme deliverables.

Clinical Outcomes

2.20	This report includes an update for the clinical indicator measures for October and November 20221.  It has been agreed that for Q3, given the transition from Digital Pen to ePCR clinical records that only October and November data will be published. This will enable the Clinical Audit and Effectiveness Department to assure the quality of the data in the new system.  The data for October and November was published in January 2022.

2.21	Currently, WAST reports on seven clinical indicators.  Five of these are care bundles for specific conditions; a care bundle requires each and every specific criterion of care to be met.

Six of the clinical indicators have a commissioning intention of 95%, the exception being the return of spontaneous circulation (ROSC) indicator.

2.22	Of the six, three achieved the 95% in the period July-21 to Sept-21 (quarter two), two others were above 90%. The ST segment elevation myocardial infarction (STEMI) indicator was previously an area of concern with a temporary low of 62.3% in Feb-21, this has now improved to 79%. The Clinical Audit and Effectiveness Department (CA&ED) undertook a deep dive of the STEMI compliance, and an improvement plan was agreed and is being progressed. These percentages refer to the application of a whole bundle of care.

2.23	The percentage of patients with attempted resuscitation following cardiac arrest, documented as having a ROSC at hospital door have remained low.  For the two months reported in quarter three the rates were 10.6%.  Rates of ROSC are complex and determined by a number of factors which contribute to the chain of survival, including speed of response, the application of early defibrillation and chest compressions.  These factors can include location of the incident, resource availability (including Community First Responders), public access defibrillation, and willingness of bystanders to engage in resuscitation. As part of its plans, WAST has developed the concept of Cymru High Acuity Response Units (CHARU) (see section: Forecasting & Modelling: Strategic Demand & Capacity Reviews).  This concept is in place in several areas across the UK and has been very successful in increasing ROSC rates. These units supplement the response to critical incidents and are crewed by a mix of Senior Paramedics and selected paramedics, maximising the provision of enhanced clinical care and ensure the consistent delivery of core critical care requirements across the whole of Wales. The CA&ED are conducting a review of the ROSC rates to determine where future improvements can be made. This will report through the Clinical Intelligence Assurance Group (CIAG) to the Clinical Quality Governance Group.

2.24	A new chronic obstructive pulmonary disease (COPD) clinical indicator has been developed to support the Band 6 Paramedic project.  The onward referral aspect of this indicator is work in progress and forms part of the national COPD pathway development.  The CA&ED have undertaken a benchmarking exercise to test the COPD Clinical Indicator which has been presented to the Clinical Intelligence Assurance Group.  The testing highlighted the requirement for significant manual scrutiny of all COPD Patient Clinical Records and the need to refine the criteria to automatically capture more of the data.

Feedback from the Group will finalise the required criteria, Health Informatics can then develop the reporting dashboard.

2.25	Discussions have commenced with EASC for the transition from Digipen to ePCR data when reporting AQIs. Seven areas for future clinical indicators have been recommended and will be processed through the appropriate governance route before a more detailed plan can be developed.

2.26 The longer term ambition for WAST is to link its patient and computer aided dispatch (CAD) data with health board patient data so that WAST can report on agreed time-based aspects of clinical indicators and track the eventual patient outcome once conveyed into a hospital.  The ePCR project will be critical to delivering this ambition. A of 7th March 2022, the ePCR is live across all bar one Health Board area, with plans for the complete roll-out to be completed by mid-Mar-22.  There are also plans for the roll-out of the necessary digital handover for hospital sites across the border into England.

EASC is asked to NOTE that: the Red 65% target was not achieved in Jan-22 (and has not been since Jul-20); Amber waiting times remain very long; these delayed responses are impacting on patient safety; in the last three months 71 patient safety incidents were reported to health boards (under the Appendix B arrangements) and 18 NRIs were reported to Welsh Government by WAST; and the ST segment elevation myocardial infarction (STEMI) indicator was previously an area of concern with a temporary low of 62.3% in Feb-21, this has now improved to 79%.

2.27	WAST is commissioned by EASC for two patient flows (journeys) within the unscheduled and scheduled care systems: the 999 Emergency Medical Services (EMS) and the Non-Emergency Patient Transport Service (NEPTS). These patient flows and their safety are now looked at in turn.

EMS Performance

Response Times

2.28	As outlined earlier in the report, response times for both Red and Amber incidents remain too long.

2.29	There are a range of factors that affect response times:

- Demand: comparing demand is difficult because of the pandemic, but WAST has previously identified that Red demand has increased significantly over the last few years. This is a major contributing factor in relation to Red performance.  In collaboration with the EASC Team at the NCCU WAST reopened the EMS Demand & Capacity Review to update the strategic modelling with this change (see 2.39) which has led to the new CHARU resource being included in the roster review keys.  Whilst there is a long term trend of increasing Red demand it did reduce in Jan-22 compared to previous months in the winter.

- Overall demand has also seen a long term increasing trend, and like Red demand, one that has been increasing faster than that forecast in the 2019 EMS Demand & Capacity Review, however, overall demand has declined in the last two months and was 6% lower in Jan-22 compared to Jan-20. This reduction in demand correlates with similar reductions in previous CoVID-19 waves.

- The number of Response hours produced: with the continued implementation of the PIP and support from the fire & rescue services, the military and St John total actual ambulance hours (all resource types) was 127,780 hours (the highest recorded) in Jan-22 with emergency ambulance (EA) unit hours production at 106% in Jan-22, unscheduled care service (UCS) production at 97% and Rapid Response Vehicles (RRVs) at 84%; RRV production was lower due to a tactical focus on conveying resource.  Whilst conveying resource production is holding up with the support from external partners the situation in quarter 1 2022/23 is now a major concern, as this support will largely stop.

- Roster abstractions, in particular, sickness absence: the Operations Response sickness absence rate in Jan-22 was 14.88%. There is significant variation within this overall percentage. The biggest cause of overall sickness (in Jan-22) is chest and respiratory problems, accounting for 22%, followed by anxiety / stress / depression /other psychiatric illnesses, accounting for 19%. WAST is concerned about the burnout and mental fatigue in its workforce.  WAST has extensive and comparatively good arrangements for managing absence and well-being including access to psychological support and a long CoVID-19 programme. For Jan-22 total abstractions off Response rosters were 41% (benchmark 30%) and 35% for its clinical contact centres (CCC), which is impacting on call performance. WAST gave a presentation at the Feb-22 CASC Assurance meeting on its structured absence management programme which forms a major part of its IMTP.

- The number of hours lost each month due to hospital handover delays. See paragraph 2.13 above.

- Multiple variables: in dialogue with the CASC, WAST has identified up to 23 “suspected” variables that impact on performance, with four: demand, utilisation, handover and time as scene considered key. This analysis has led to the innovative development of a pilot measure of ambulance unit hours utilisation (UHU), which the CASC has started to share more widely with stakeholders since Sep-21 and is reported internally within WAST.

- Post production lost hours (PPLHs): 14,279 hours were lost post production in Jan-22, although this data is subject to a variety of caveats and ongoing internal reviews of the data accuracy.

PPLHs include a range of reasons e.g. vehicle defect, trauma stand down, police interview, etc. which cannot be viewed as areas for potential efficiencies.  The EMS Demand & Capacity Review identified that WAST benchmarked comparatively well on PPLHs with the exception of return to base meal breaks. EASC members will note the dark blue data in the graph which forms a significant proportion of the total, which relates to lost hours due to increased HALO duties, which are required and utilized at times of high pressure within EDs. WAST has undertaken some recent benchmarking with three other ambulance services, two of which WAST benchmarks favourably with whilst the third is significantly better.  WAST re-started (08 Sep-21) negotiations with TU partners on a collaborative solution for return to base meal breaks (and other workforce practices). This work has identified issues with data accuracy that are currently being addressed.  WAST Executives have recently received initial outputs from the negotiations which are currently under consideration.

2.30	WAST is also engaged in a number of programmes across the unscheduled care system which are designed to shift demand left including: the core 111 service was launched in BCUHB on the 22 Jun-21.  The roll out of the core 111 service in C&VUHB is currently planned to be completed by the end of March 2022. WAST has received non-recurring financial support from EASC to expand the Clinical Support Desk (CSD) which will see an increase in mental health professionals and 36 FTE Paramedics.  These increases will support hear & treat, but also patient safety netting and other related activities.

The CASC has requested an evaluation of the impact of these additional CSD FTEs.  This recruitment is complete.  The CSD and NHSDW (Hear & Treat) achieved a combined rate of 11.0% in Dec-21.  The EMS Demand & Capacity Review identified a benchmark of 10.2% (modelled to be achieved by Dec-21) which will be revised up to 15% as a result of this increase.  Discussions are ongoing in relation to recurrently funding this resource

2.31	​If mitigating actions agreed / funded are not sufficient to manage patient demand WAST (which currently they are not) WAST will enact its Clinical Safety Plan previously known as the Demand Management Plan.  The CSP aligns with the Association of Ambulance Chief Executives (AACE) approved UK Clinical Safety Plan Framework requiring members to realign their existing plans to provide national consistency in the definition and reporting levels.  WAST has seen increased use of the higher levels of the CSP (level 4) which means “unable to send” to Amber 2 and Green incidents; for the 30 days to 14 Feb-22 WAST was at level 4 for 2 of the 30 days.

EASC is asked to NOTE that: WAST continues not to achieve the Red 8 minute 65% target,; WAST did achieve Red 10 minutes 65% of the time in Jan-22; that there are a range of factors coalescing to affect Red (and Amber) performance; WAST has boosted ambulance production through support from external partners; WAST is drilling into the PPLH data to more accurately quantify the potential efficiency around return to base meal breaks; WAST is further expanding CSD capacity to shift demand left; and patient safety in quarter one is now a major concern because system pressure is expected to remain high, but the current ambulance production mitigations will have ceased.

Ambulance Care (including NEPTS)

2.32	The NEPTS ambulance quality indicators have now resumed reporting.  Key points about NEPTS are as follows:-

- CoVID-19 saw a significant drop-in patient transport activity at the start of the pandemic. Levels have increased, and are at or in excess of pre-pandemic levels for all journey types apart from outpatient journeys; however, the overall level of activity has still not recovered to pre-CoVID-19 levels due to the reduction in outpatient activity;

- CoVID-19 abstractions and social distancing have been challenging, but NEPTS has seen a continued improvement in key areas of service delivery particularly discharge and transfer journeys;

- Enhanced services performance is above target for renal and is improving for oncology (area of review);

- Social distancing means that the number of patients that can be transported per journey has reduced, which has a significant impact on NEPTS capacity;

- In the first wave there was a significant reduction in outpatient transport activity, which meant that the impact of CoVID-19 on NEPTS capacity could be offset by the reduced demand; however, core demand is now on a clear upward trend;

- NEPTS capacity is also adversely affected by other CoVID-19 factors: journeys taking longer due to PPE, staff sickness and need to provide alternative duties to high-risk staff, staff training and testing, infection prevention and control arrangements and so on;

- NEPTS continues to liaise closely with the commissioning process and the final transfer of works (CTMUHB) has recently been completed; and

- NEPTS performance has been supported by in-year funding which is due to cease on 31 Mar-22. WAST is writing to the CASC requesting that this funding continue.

2.33	79% of core journeys arrived within 30 minutes (+/-) of their appointment time in Jan-22; 82% of enhanced renal journeys arrived within 30 minutes prior to their appointment time; and 64% of enhanced oncology journeys arrived within 30 minutes prior to their appointment time. Oncology has been identified as an area of focus from the NEPTS Demand & Capacity Review and will require changes in the way WAST works with the voluntary and community sector (VCS) to improve performance.

2.34	There is a Welsh Government ambition to see outreach appointments reduce by 50% “in time” (Health & Social Care in Wales – CoVID-19: Looking Forward); however, the short term scenario is that as the health care system emerges out of the pandemic response in 2022/23 this may see pent up demand for NEPTS as the system is switched back on and tries to catch up on certain services. This is a significant risk to the system as social distancing/PPE has reduced Ambulance Care capacity. WAST modelled this scenario and reported the results and impacts to the CASC. WAST subsequently received in year investment to boost NEPTS capacity, in particular, the recruitment of drivers and procurement of external providers.  This additional capacity is in place and applies until 31 Mar-22.  Further consideration is being given by the NCCU and WAST as to what happens post the 31 Mar-22.

2.35	Finally, the NEPTS Demand & Capacity Review is complete and WAST has now established an Ambulance Care Transformation Programme Board, which includes recommendations from the Review and other key transformation work. Both health boards and the EASC Team are represented on the Board.  The programme is a significant body of work including pan-Wales roster reviews (ambulance transport and NET call centre), options for improving oncology performance times, testing approaches for efficiency improvements linked to outpatient outbound ready times, CAD updated/replacement and so on.  WAST is making good progress on the programme; however, the original plan to re-roster NEPTS transport in 2022/23 is expected to change because of the complexity of re-rostering against a demand pattern that is unstable.  WAST has discussed this with the NCCU and the current plan is to undertake further work on agreeing a set of roster keys, with implementation now expected early in 2023/24.

EASC is asked to NOTE that: NEPTS capacity is being boosted through in-year investment to mitigate the risk of reduced capacity caused by CoVID-19 and to aid system flow; performance has been maintained, but with oncology being an on-going area of concern; further consideration needs to be given to what happens when the in-year investment stops on 31 Mar-22; the Ambulance Care Transformation Programme has been established and is making good progress; and the revised plan is now to undertake more detailed pre-work on NEPTS re-rostering in 2022/23 with the potential go live being in 2023/24.

Commissioning, Planning and Service Change

Forecasting & Modelling: Strategic Demand & Capacity Reviews

2.36	The EMS Operational Transformation Programme (arising from the EMS Demand & Capacity Review) is WAST’s main strategic response to patient safety and experience concerns for the EMS five step ambulance care pathway. In addition to the EMS Demand and Capacity Review recommendations three other IMTP actions – CHARUs, Rural Model Pilot (in Powys) and Leading Service Change Together (modernisation of working practices) have been brought under the umbrella of the programme.

2.37	EASC had delegated oversight of the delivery of the programme to EASC Management Group. WAST is making good progress on the recruitment and training aspect of this programme.  The original 20-22 recruitment and training target i.e. closing the relief gap, was 1,691 FTEs.  WAST’s 31 Mar-22 forecast is 1,680 FTEs, including the uplifts into the CSD. WAST is also boosting its 999 CCC call handling capacity; however, the current rate of attrition is working against delivering this uplift by Feb-22 as planned (on-target for Mar-22).

2.38	Other key aspects of the programme include re-rostering CHARU/EAs and UCAs pan-Wales. The rostering project was paused to consider further modelling information linked to changing Red demand, lost hours in the system and feedback from stakeholders, but has now restarted with the CHARUs (unfunded at this time) built into the roster keys.  WAST has undertaken a Rural Impact Assessment pan-Wales, which it has shared with the Deputy Chief Ambulance Services Commissioner (DCASC). This assessment identified a positive impact in all areas defined as rural by Welsh Government.  WAST continues to work with TU partners on workforce practices via the Leading Service Change Together approach.

2.39	In Aug-21 the CASC agreed to re-open the EMS Demand & Capacity Review to look at the period 2022-25.  Initial modelling on the CHARU concept has been completed (and built into the re-rostering project) with a Transition Plan business case developed for 2022/23, designed to put  CHARU, APP and EA capacity into the system, to help offset the impact of handover lost hours.  The Transition Plan also represents the next steps towards a more radical and transformed service model for Wales to be implemented over the coming 2-3 years.  WAST is expecting the modelling for this to be available in late Jan-22 (received), with the DCASC included in this process, and the final formal steering group meeting arranged for Apr-22.

Commissioning Intentions

2.40	The Dec-21 EASC Management Group did not meet, but the EASC Team at the NCCU and WAST collaborated on a joint report on WAST’s progress on the 2021/22 intentions. WAST is considered to have made good progress and will report its year end position to Apr-22 EASC Management Group.

2.41	WAST has also been in dialogue with the NCCU on the draft 2022/23 EMS and NEPTS commissioning intentions and is broadly supportive of these, in particular, a continued focus on being clinically led, shift left, workforce stabilisation and workforce availability.

Integrated Medium Term Plan (IMTP)

2.42	The WAST IMTP is delivered through a portfolio of transformation programmes supported by enabling programmes, projects and workstreams, which align to both WAST strategic ambitions and commissioning intentions. Despite the continued operational pressure and the need to pause some work on the IMTP there has been continued progress across our major programmes of work.

2.43	EMS Operational Transformation Programme:-

- Recruitment and training is on track to close the relief gap early in 2022/23 ,subject to funding of backfill from additional CSD clinicians;

- The roster review project has been re-commenced and due to go live during September to November;

- Leading Service Change Together project requires further discussion with Trade Union partners as we understand outcomes of benchmarking, modelling and a data quality review;

2.44	Looking forward to 2022/23, a major element of the Trust’s IMTP will be the proposals set out in our Transition Plan, submitted to the CASC in late Dec-21. The Trust is committed to doing all that it can to reduce clinical risk, improve patient care and outcomes, and to playing an increasing role in a transformed urgent and emergency care system, ensuring that patients get the right service, in the right place, every time. The case proposes additional investment to increase front line capacity across the Emergency Medical Service (EMS) enabling the capacity to begin transformation of services that can support a shift left in the five step model, doing more through hear and treat and see and treat in line with WAST strategic ambitions.

This is a critical step towards a transformed model of ambulance services, which if funded could deliver the following benefits:

- an increased capacity and resilience in our core service to meet the needs of the population of Wales in a safe and timely way, improving outcomes for patients and reducing clinical risk and harm;

- an improvement in the working lives of our frontline staff, alleviating the causes of stress and sickness and further improving our ability to provide the required capacity;

- a transition away from the traditional model of ambulance services, towards a transformed state in which patients are increasingly treated at or near home, avoiding unnecessary conveyance to an Emergency Department (ED), improving patient outcomes, and relieving pressure within the urgent and emergency care system;

- a realignment of resources, ensuring that their value is maximised in the most effective and efficient way to meet patient needs.

2.45	Ambulance Care:-

- Taking forward the NEPTS Demand and Capacity Review a PID has been developed for a Roster Review project and a case developed for additional 12 FTEs in planning and day control subject to funding through the IMTP;

- Following the completion of health board transfers of work, the next stage of the Plurality Model project is to develop a Procurement Strategy, for which work has already commenced;

- The extension to the Grange Hospital Commissioning Agreement is nearing its end, and meetings need to be commenced to determine the future commissioning arrangements for the transfer service within ABUHB;

- The refreshed PNA (Patient Needs Assessment) launched on 01 Dec-21 and an alternative options search tool has been added to the NEPTS website; and

- The operational improvement plan is making steady progress in its four key domains.

2.46	Strategic ambition programmes:-

- The transformation programmes for EMS and Ambulance Care are supported by two further core service transformation programmes: Gateway to Care focusing on 111 and the implementation of the CCC Clinical Review; and Clinical Transformation with a focus on the clinical transformation required to shift left in the five step model;

- Our enabling programmes and workstreams are focusing on our people, estates, fleet and digital enhancements required to support IMTP delivery and commissioning intentions as well as the strong partnerships required to support system wide improvement across Wales, research and innovation activity and our;

- The ECNS is on track and the CSD Roster Review complete;

- ePCR has rolled out across Wales with some final adjustments to be made to align to local health board systems ahead of the decommissioning of DigiPen at the end of March;

- WAST’s new Consultant Paramedic has commenced in post and is already taking forward the clinical transformation agenda;

- WAST held a follow up workshop in Feb-22 to further develop its thinking around our full strategic ambitions in EMS: "Inverting the Triangle" concept. The DCASC was again involved in the workshop which focused on the workforce, organisational development and cultural change required to achieve this ambition as well as the key stakeholders with whom WAST would need to work to garner support for the proposed changes;

- There has been continued engagement with the WG and health boards in relation to Same Day Emergency Care (SDEC) proposals and how WAST can support the six goals programme in delivering SDEC;

- There have been ongoing discussions with ABUHB to explore the option to expand the COPD pathway to breathlessness; and the development of a SOP and flowchart with SBUHB;

- Non-Injury Falls Pathway: Digital Solution agreed and updated via TerraPACE app, but will require testing in Q4 prior to implementation;

- Other enabling programmes: WAST continues to make good progress supporting staff and delivery of the IMTP. WAST is close to finalising the new corporate accommodation and NEPTS station at Beacon House in Cwmbran which will be the base for the Grange Transfer service. Progress continues on the reconfiguration of Vantage Point House as an operational hub, and Cardiff Ambulance Station is close to completion. Our fleet replacement programme is on track and digital infrastructure continues to be rolled out, in support of major new operational systems including ePCR, ECNS and SALUS. Further development of our infrastructure will be required if the Transition Plan is funded.

- Recovery planning is currently focusing on the key actions we will need to take to either stand down or evolve the systems, policies, products etc. that were put in place during the pandemic. This includes the guidance we give to staff around infection prevention and control measures (such as PPE, social distancing etc.) and their impact on our infrastructure requirements in the medium to long term.

2.47	Value Based Healthcare:-

- WAST has been fully engaged with the EASC Team at the NCCU in development of Commissioning for Value and internally will align the development of its own value based approach to demonstrate value for investment, whilst widening the remit to include quality improvement, staff and patient  outcomes and experience and sustainability as measures of value. There will be a renewed focus on Value and the implementation of the Patient Level Information Costing system (PLICs) which will help us identify areas of variation in WAST’s IMTP.

Health Board Changes

2.48	WAST continues to support Regional developments including vascular centralisation in South Wales. Following a readiness assessment it has been agreed by the programme board that the go live date be pushed back to Jun-22. WAST also attended a recent national Thrombectomy commissioning workshop and has implemented a system, agreed with the South Wales Major Trauma network, for clinician agreement through the Major Trauma desk to transfer patients to a Thrombectomy centre in a timely manner to ensure the Thrombectomy window of opportunity is met more frequently.

Transferring patients for major trauma, stroke, PCI, vascular and other time critical transfers are hindered by the delays experienced outside EDs. WAST has tested the market to establish short term provision of a private service to undertake these time critical transfers. The results will be communicated to the DCASC shortly, with a view to considering the opportunity for a longer term service pending the development of a national model of transfer and discharge services for which WAST would aim to be the provider of choice as set out in its IMTP.

2.49	There is emerging changes in Shrewsbury and Telford cardiac and stroke services impacting on the primary conveyance destination of a number of areas of Powys. WAST is engaged with Powys to model the impact of the changes and agree clinical safeguards to ensure patients can access emergency care as close to home as possible, in a timely way. Further information will be reported to WAST’s Integrated Strategic Planning Group in due course and we will provide any updates required to the DCASC.

2.50 	WAST’s Integrated Strategic Planning Group has been re-established and will have oversight of health board operational and strategic service changes to comprehend and coordinate implications on WAST and for WAST to support these plans. WAST is currently updating our service change map for inclusion in the IMTP.

EASC is asked to note that: WAST continues to make good progress in delivering its IMTP and on its 21/22 commissioning intentions; the re-rostering project is due to go live between Sep-22 and Nov-22; WAST continues to work with TU partners on modernising working practices following a brief pause over winter; a Transition Plan for 2022/23 has been developed and presented to the CASC with further modelling undertaken to understand the impact of “Inverting the Triangle” in 2023-25; WAST has aligned its IMTP to the updated NCCU IMTP and EASC commissioning intentions; and WAST continues to make good progress on a range of transformation programmes and actions designed to improve patient safety for EMS and Ambulance Care and support the wider health care system, despite continued pressure across the system.

Conclusions and Forward Look

2.51	Current performance levels and patient safety remain very challenging.

2.52	WAST is focused at an organisational level on this challenge and is being supported through the commissioning process.  WAST is currently as level 3 escalation, is pro-actively managing patient demand (and safety) through enacting its Clinical Safety Plan (demand management arrangements) and shift left actions, will shortly stand down its Pandemic Plan structures, is boosting capacity through a range of in year investments, has boosted capacity through the support of key partners (fire & rescue services, military and St John) and is boosting capacity through the delivery of efficiencies. All of this work is brought together into WAST’s PIP, which is formally reported on every two weeks to the CEO with the CASC reporting to the Minister each month.

2.53	However, whilst WAST has been able to boost production during the winter period, quarter one 2022/23 is now a major concerns as the vast majority of the actions designed to boost production will have ended, but system pressure is expected to remain high. WAST has written to the CASC requesting the continuation of funding in support of tactical mitigations.  The Transition Plan offers an interim mitigation whilst the “inverting the triangle” offers the system a transformative approach to improving patient care/outcomes whilst reducing pressures on DGHs.

- KEY RISKS/MATTERS FOR ESCALATION TO THE COMMITTEE

Members of the EAS Committee are asked to note that:

3.1	CoVID-19 and the impact of CoVID-19 is having a severe impact on WAST, in particular, high roster abstractions, high handover lost hours and social distancing on NEPTS transport;

3.2	WAST is at escalation level 3 and expects to remain so for the foreseeable future, but WAST does expect to stand down its Pandemic Plan structures shortly;

3.3	Quality, safety and patient experience monitoring arrangements have continued (and been enhanced) through the pandemic. WAST remains very concerned at the patient safety risks associated with response times that are too long;

3.4	There were 503 12 hour and over patient waits in Jan-22 (the second highest recorded), 71 patient safety incidents were referred to health boards under the Appendix B arrangements) over the last three months and 20 WAST NRIs were reported to Welsh Government;

3.5	The Red 8 minute 65% target has not been hit since Jul-20 (65% of Red incidents were responded to in 10 minutes in Jan-22);

3.6	With support from external partners WAST has been able to deliver its highest recorded level of ambulance hours (all resource types), but in Jan-22 WAST lost 22,563 to handover delays (or 1,962 ambulance shifts), a level that WAST cannot offset without radical measures to shift left or improve system flow;

3.7	WAST has produced a Transition Plan for 2022/23 to increase capacity, continue to make improvements in efficiency and to further increase numbers of APPs and has undertaken modelling on a radical shift left;

3.8	WAST continues to seek efficiencies, in particular, the pan-Wales EMS Response roster review and modernising working practices;

3.9	The ePCR programme has gone live and is now being rolled out pan-Wales;

3.10	NEPTS has received £2.0m investment to boost capacity to support system flow which it has deployed, but this funding ends on 31 Mar-22;

3.11	An Ambulance Care Transformation Programme Board has been established to take forward the findings of the NEPTS strategic Demand & Capacity Review and wider NEPTS and transfer and discharge projects;

3.12	WAST is making good progress on its IMTP ambitions (including the EASC 21/22 commissioning intentions);

3.13	3.14	WAST continues to engage with health boards on a range of service re-configurations that affect ambulance provision; and

3.15	There is major concern about patient safety in quarter one 2022/23 and a tactical focus on it i.e. what happens when some of the current actions to boost both EMS and NEPTS capacity cease and system pressures whilst reduced from mid-winter, remain high.

- IMPACT ASSESSMENT

| Quality/Safety/Patient Experience implications | Yes (Please see detail below) |
| --- | --- |
|  | Identified within the report |
| Related Health and Care standard(s) | Timely Care |
|  | And all health and care standards |
| Equality impact assessment completed | Not required |
| Legal implications / impact | There are no specific legal implications related to the activity outlined in this report. |
|  | Included within the body of the report |
| Resource (Capital/Revenue £/Workforce) implications / Impact | Yes (Include further detail below) |
|  | Included within the body of the report |
| Link to Main Strategic Objective | The Committee’s overarching role is to ensure its Commissioning Strategy for Emergency Ambulance Services utilising the five step patient pathway outlined within the National Collaborative Commissioning Quality and Delivery Agreement and the related outcomes for each care standard aligned with the Institute of Healthcare Improvement's (IHI) ‘Quadruple Aim’ are being progressed. This report focuses on all the above objectives, but specifically on providing strong governance and assurance and safe and effective patient care |
| Link to Main WBFG Act Objective | Service delivery will be innovative, reflect the principles of prudent health care and promote better value for users |

- RECOMMENDATION

5.1	The EASC Committee is asked to:

- DISCUSS and NOTE the WAST provider report.