| Ref | EMRTS Commissioning Intention 1: Service Expansion | Date | RAG | Update |
| --- | --- | --- | --- | --- |
| CI1a | Enhanced CCP-led response – Building on the implementation of an enhanced daytime response from Cardiff Heliport in April 2022, the EMRTS will focus on managing the ongoing service delivery with a view to demonstrating the more effective use of resources, improved service quality and the patient experience and opportunities for workforce development. | 31st March 2024 |  | This service is operating well. The work force resourcing includes a Critical Care Practitioner (CCP) shift lead who is guiding practitioner development through live mentoring. Patients are receiving a range of enhanced treatments including autonomous blood product administration, procedural sedation, post ROSC care and additional medications that sit outside JRCALC. This enhanced CCP response is working collaboratively with Specialist Paramedic and CHARU (Cymru High Acuity Response Unit) colleagues in WAST supporting practice and adding value where required. We continue to provide a transfer capability to CHANTS/Watch Colleagues (neonatal and paediatric transfer services) as required. Given the proximity of our CCP team in the South East area the forecasted protection of the Physician lead team in Llanelli has been realised, this has proved valuable in being available for wider taskings across the region/ Wales. Data collection is complete for the first year of operation and will be analysed shortly pending completion of the ACCTS service evaluation. |
| CI1b | Evaluation and Review – Evaluation and review for the enhanced CCP-led response to be incorporated to the ongoing process of evaluation already in place within the service. | 31st March 2024 |  | A CASC process of engagement the ‘EMRTS Service Review’ commenced in February 2023. The CASC review has entered its third and final phase of engagement. Phase 3 will run from 1st-29th Feb. No further activity is being undertaken until the outcome of this review has concluded. |
| CI1c | Planning – Build on the implementation and consolidation of Phase 1 of the EMRTS Service Expansion project, working collaboratively. with commissioners to plan the implementation of the remaining phases of the EMRTS Service Expansion programme. | 31st March 2024 |  | EMRTS Service Expansion project will follow on from the completion of CASC Service Review and align with its outcome. |
| Ref | EMRTS Commissioning Intention 2: Adult Critical Care Transfer Service Implementation | Date | RAG | Update |
| CI2a | Service Delivery – The ACCTS team will continue to manage ongoing service delivery and will ensure robust performance management with a focus on outcomes, value, quality and safety of service delivery. | 31st March 2024 |  | ACCTS is delivering more than forecasted activity between our North and South Wales resources. The Service continues to host Clinical Governance Days and regularly contributes to the EMRTS Delivery Assurance Group. Ongoing issues with ACCTS Base provision in North Wales. Alternative options are being assessed. |
| CI2b | Engagement – Continue to build on established relationships and to engage with all stakeholders to review and strengthen the service model(s) implemented to maximise the clinical outcomes, value, quality and safety of service delivery. | 31 March 2024 |  | The service continues to deliver for capacity pressures, time critical transfers and escalation of care. Due to ongoing financial constraints the overnight on-call provision for North Wales has been suspended. The provision was a temporary measure and provided without any additional funding. There are ongoing challenges to match ACCTS activity to the demand in North Wales. Engagement with Heath Boards and Commissioners is ongoing, and a review is required regarding how the service is managed in that particular area. |
| CI2c | Evaluation and Review – Undertake evaluation and review relating to the implementation of the ACCTS, reporting on lessons learned, service activity and providing the required assurance regarding the realisation of anticipated outcomes and benefits going forward. | 31st March 2024 |  | A review of Year 1 was undertaken in Quarter 3 22/23. Part of the organisations culture of continuous learning and improvement, an internal lesson learnt exercise also took place engaging with multiple stakeholders and the recommendations have been implemented. ACCTS provide a Clinical Governance Day that any stakeholders can join. Evaluation of the service continues and will ensure any further improvements required are assessed appropriately. A full ACCTS Evaluation Report will be presented at the next DAG in March 2024. |
| CI2d | Quality and Delivery Framework – As an established service hosted by the EMRTS, work will now be undertaken with the EASC Team to ensure that a collaborative commissioning framework is now developed specifically for the ACCTS. | 31st March 2024 |  | Ongoing development for Quality & Delivery Framework and CAREMORE specific for ACCTS. Subject to ACCTS Service Evaluation and the wider EMRTS Service Review. |
| Ref | EMRTS Commissioning Intention 3: Service Evaluation | Date | RAG | Update |
| CI3a | Ongoing Evaluation – Building on the 5-year EMRTS Service Evaluation (2015-20) develop a programme of ongoing evaluation including robust methodology | 31st March 2024 |  | The EMRTS Service Review has completed Phase 2 of the Engagement Process. The 3rd and final phase will take place between 1st and 29th February 2024 for public feedback. Until the outcome of the review is known an Improvement Plan cannot be developed. |
| Ref | EMRTS Commissioning Intention 4: System Transformation | Date | RAG | Update |
| CI4a | Demand and Capacity Strategy – To continue with the work on a collaboratively developed demand and capacity strategy will set out the ongoing arrangements for proactively undertaking this work for the next decade, this will include the use of forecasting, modelling and health economic evaluations. | 31st March 2024 |  | Following a formal Demand & Capacity review by the service and because of recommendations, CASC are conducting a formal review of the Service Development Proposal submitted by EMRTS. The EMRTS Service Review is in phase three and once complete will inform next steps for both organisations. |