# EASC Key Deliverables

| EASC | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| --- | --- | --- | --- | --- | --- |
| EASC New Normal Activity by Quarter | EASC Governance - EASC Standing Orders created, adopted and complied. - Preparation of the Annual Governance Statement for EASC. - Preparation of the Annual Quality Statement for EASC. - EASC meetings reinstated from 12/05/20 following suspension due to COVID19. - EASC Management Group reinstated June 2020 - NEPTS DAG meetings reinstated bi-weekly from 29/04/20 following suspension due to COVID19. - Develop EASC Risk Management Framework and risk register documentation. - Every EASC subgroup meeting to have: - Agenda in the EASC style - Action notes - Action log - Highlight report after every meeting - Forward plan of business | EASC Governance - Completed EASC Annual Report (Finance & Activity EMS, NEPTS & EMRTS). - Development and undertaking of External / Internal Audit work plans for EASC. Embedded research capability - Complete Memorandum of understanding with Swansea University for C3 Faculty. Strengthening Winter Resilience - EASC Chair Objective: Review and agree further EASC actions to underpin winter planning 2019-20. - Q2 EASC TEAM will disseminate Winter learning to support winter/COVID19 planning for 2020/21 | IMTP Guidance - The production of annual commissioning intentions for EMS, NEPTS and guidance support for EMRTS. - Support Health Boards; WHSSC and Velindre NHS Trust’s IMTP production process. - Q3 EASC / NPUC Commissioning Intentions and alignment with IMTPs 2022/22 process and associated documentation was produced by the EASC TEAM in support of both EASC and the NPUC. - Q3 Share progress of IMTP Responses to the EMS & NEPTS Commissioning Intentions with Policy Le ads within Welsh Government EASC Enhanced Assurance - Operation and enhancement of the electronic Benchmarking Toolkit. Embedded research capability - C3 Recruit EASC researcher from Healthier Wales EASC Commissioning Allocation. Strengthening Winter Resilience - Q3 Share learning from Evaluation of winter monies evaluation with Welsh Government & Health Boards Government |  | IMTP Guidance - The sharing of EMS NEPTS EMRTS commissioning intentions across Welsh Government & Health Boards. - Review and subsequent recommendation for approval of the WAST IMTP - Submission of EASC IMTP to Welsh Government. Embedded research capability - Develop C3 work programme for EASC. |
| EASC New Normal Activity Q1-4 2020/21 | EASC Governance - Model EASC Standing Financial Instructions awaited - Produce reports required by the EASC Meetings to effectively discharge its responsibilities. - Deliver the EASC information management requirements of: - meeting the expectations of EASC being a designated official publisher of statistics through its submission of accurate Ambulance Quality Indicators (AQIs) for publication by Stats Wales; - designing the EMS, NEPTS and EMRTS data repositories including the reporting of what, when and to whom - supporting the use of the data repository in reviewing and analysing EMS NEPTS EMRTS performance - development of a comprehensive suite of performance and outcome measures across clinical, patient experience and value for money which are regularly reported - acting as the conduit between WAST and HBs for EMS NEPTS and EMRTS for the development and then reporting of local measures relevant for Health Boards’ populations EASC Enhanced Assurance - Reporting of any findings in relation to quality assurance and improvement of the EASC commissioned service of EMS which may come to light through the EASC Management Group. - Reporting of any findings in relation to quality assurance and improvement of the EASC commissioned service of NEPTS which may come to light through the NEPTS Delivery Assurance Group. - Reporting of any findings in relation to quality assurance and improvement of the EASC commissioned service of EMRTS which may come to light through the EMRTS Delivery Assurance Group. - Consideration and subsequent implementation of any actions arising following internal and external audit reviews. EASC Commissioning - Delivery of the improvements to the EMS & NEPTS Quality & Delivery Framework as specified within Commissioning Intentions 2020/21 and agreed as part of the EASC and WAST IMTP 2020/21 Alignment process and its associated documentation - Delivery of EMS & NEPTS performance improvements by WAST as specified within Commissioning Intentions 2020/21 and agreed as part of the EASC and WAST IMTP 2020/21 Alignment process and its associated documentation - Delivery of EMS & NEPTS performance improvements by both WAST and Health Boards / Velindre NHS Trust / WHSSC (Renal Network) as specified within Commissioning Intentions 2020/21 and agreed as part of the EASC and WAST IMTP 2020/21 Alignment process and its associated documentation |  |  |  |  |
| EMS new normal activity | COVID 19 Pandemic Response - EASC Team will continue to assess support WAST EMS Pandemic response. - EASC Chair Objective: Undertake demand and capacity assessment of WAST for system discussion and actions - Q1-4 Utilising modelling and D&C profiles to support the system returning to the new-normal - Q1 WAST D&C modelling supported HB field hospital/surge capacity Ministerial Ambulance Availability Taskforce - Capture learning & good practice from COVID around ambulance availability, workforce, and digital. | EASC Enhanced Assurance - Determine the resources needed in support of EASC’s enhanced requirements. And the establishment of EASC Quality Assurance & Improvement Services EASC Governance - EASC & CASC MOU with Welsh Government revised. - Continued challenge & scrutiny by EASC Management Group on behalf of EASC reinstated following suspension due to COVID19. | EASC Commissioning - Production of EMS annual commissioning intentions 2021/22 - 6 monthly Commissioning intention progress report Q3 2020/21 EASC Enhanced Assurance - Establishment with the use of additional resources a quality assurance and improvement service for EASC commissioned services of EMS and NEPTS which will include: - incidents and complaints reporting and reviews; - daily performance reviews; - Clinical risk assurance reviews. Enhanced assurance on finance & performance to both Welsh Government & EASC by CASC; - Delivery, management and control of Demand & Capacity Review's findings Ambulance Productivity Task Force Ministerial Ambulance Availability Taskforce - Review scoping document produced. - Progress report to the Minister. |  | COVID 19 Pandemic Response - EASC Team will review WAST EMS Pandemic response Ministerial Ambulance Availability Taskforce - Taskforce Initial Report |
|  | COVID 19 Pandemic Response EASC Team Supporting WAST Pandemic Response - CASC support & EASC endorsement for WAST pandemic response plan. - Health Board Surge capacity through daily pandemic calls & WAST Cell structure. - Monitoring WAST COVID19 spend with FDU. - Coordinating non-emergency field hospital step down transport through the NEPTS DAG. - Supporting HB surge capacity planning through transport modelling. - EASC Team supporting Welsh Government guidance production - Emergency transport guidance |  | - EASC Chair Objective: Amber Review Implementation: - Q3-4 Sustainable improvements re: number of lost hours due to handover delays to be maintained as system returns to the new normal. - Q3-4 Working with health boards to ensure that the PODs can support sustained reduction in handover delay. ` - Q3-4 EASC TEAM working with WAST to maintain current amber response times. |  |  |
| NEPTS new normal activity | COVID 19 Pandemic Response - EASC TEAM will continue to support WAST NEPTS Pandemic response through increased NEPTS DAG meetings - EASC TEAM supporting Welsh Government guidance production - Non- Emergency transport guidance - D2RA Guidance EASC Enhanced Assurance - NEPTS 19/20 Internal Audit report received. EASC Commissioning - NEPTS Demand & Capacity Review Steering Group process reinstated following COVID19 delay. | EASC Commissioning - Implementation commences for NEPTS Demand & Capacity Review. 3 month delay to original timelines. - Development of new normal return to normal service function EASC Enhanced Assurance - Commence implementation of NEPTS Audit report findings. | EASC Commissioning - Production of NEPTS annual commissioning intentions 2021/22. - 6 monthly Commissioning intention progress report. |  | EASC Commissioning - Plurality model fully enacted & all Health Board Provision transferred to WAST, Delayed 6 months due to COVID19. - Delivery of the benefits from the business case following the ‘Transfer of Work’ from Health Boards to WAST. - Transport solutions delivering WHC 2007(005). - Development of benefits realisation from the business case following the ‘Transfer of Work’ from Health Boards to WAST. |
| EMRTS new normal activity | COVID 19 Pandemic Response - EMRTS Weekly SItrep report to the CASC EASC Commissioning - Complete signing of EMRTS quality & delivery framework. - Preparation of a CASC led business case to agreed 24/7 capital funding. | COVID 19 Pandemic Response - EMRTS Weekly SItrep report to the CASC EASC Governance - Enhanced role & function of the EMRTS Delivery Assurance Group EASC Commissioning - Supporting EMRTS 24/7 expansion - Recruitment of an EASC TEAM programme Lead & EMRTS clinical lead to support the development of national critical care transfer service. | EASC Commissioning - EMRTS Inaugural Commissioning intentions 2021/22 produced - EMRTS contribution towards Major Trauma EASC Governance - Revise governance framework between EASC, Wales Air Ambulance & SBUHB |  | EASC Commissioning - EMRTS contribution towards Major Trauma |
| EASC Future Commissioned Transport Services new normal activity | National Transfer & Discharge Service - Capture learning and good practice across planning transport for Surge Capacity Field Hospitals to develop a National Transfer & Discharge Service. | National Transfer & Discharge Service - Develop programme business case. - Identify commissioning resources - Identify finance sources. Establish governance mechanisms. | National Transfer & Discharge Service - Formation of Transfer & Discharge Delivery Assurance group including governance documentation. |  | National Transfer & Discharge Service - Commence development of national commissioning framework for transfer & discharge. |
|  | Grange University Hospital - EASC TEAM Chairing and providing clinical & programme support for ABUHB/WAST/EASC weekly commissioning transport group for GUH | Grange University Hospital - EASC TEAM Chairing and providing clinical & programme support for ABUHB/WAST/EASC weekly commissioning transport group for GUH | Grange University Hospital - EASC TEAM Chairing and providing clinical & programme support for ABUHB/WAST/EASC weekly commissioning transport group for GUH October 2020 go live (COVID19 dependent) |  | Grange University Hospital - Transition GUH Transfer & Discharge services into National Commissioning Framework. |
|  | Field Hospitals - Support the system to deliver an optimal transfer and transport service for the flow of patients to and from field hospitals; |  |  |  |  |
|  | Stroke Thrombectomy Repatriation Service - Scope developed with WHSSC & WAST for stroke Thrombectomy repatriation service. - EASC TEAM Representation on the Thrombectomy Network. | Stroke Thrombectomy Repatriation Service - Implement Stroke Thrombectomy repatriation service. | Stroke Thrombectomy Repatriation Service - Service Commissioned - Monitor Stroke Thrombectomy repatriation service. |  |  |
|  | Critical Care Transfer Service - Develop business case for WG detailing the service model for all Wales critical care transfer service. | Critical Care Transfer Service - Develop job Descriptions and Recruit EASC TEAM programme support to deliver critical care transfer scoping with EMRTS. | Critical Care Transfer Service - Develop national model scope. - Business case completed - Clinical lead and project manager appointed |  | Critical Care Transfer Service - Commence phase 1 implementation. |