Non-Emergency Patient Transport Services

Delivery Assurance Group

(NEPTS DAG)

# Minutes/Action(s)

Tuesday 18 August 2020

12:00pm to 13:00pm

# Attendees (Via Microsoft Teams):

| # National Collaborative # Commissioning Unit (NCCU) | # James Rodaway (JR) – NCCU [Chair] |
| --- | --- |
|  | # Stephen Harrhy (SMH) - NCCU |
|  | # Gwenan Roberts – (GR) - NCCU |
|  | # Jonathan Jones (JDJ) – NCCU |
|  | # Debra Fry (DF) – NCCU |
| # Health Boards / Trusts / Committee | # Andrew Walsh (AW) - ABUHB |
|  | # Jennifer Green (JG) - ABUHB |
|  | # Gillian Milne (GM) - BCUHB |
|  | # Rab McEwan (RM) - BCUHB |
|  | # Meinir Williams - BCUHB |
|  | # Melanie Wilkey (MW) - CVUHB |
|  | # Gareth Skye (GS) - HDUHB |
|  | # Andrew Quarrel (AQ) - PTHB |
|  | # Joanne Jones (JJ) – SBUHB |
|  | # Jeff O’Sullivan (JS) – Velindre |
|  | # Susan Spence (SS) – Renal Network |
| # Welsh Ambulance Service Trust (WAST) | # Aaron Evans (AE) - WAST |
|  | # Bethan Roberts (BR) - WAST |
|  | # James Haley (JH) – WAST |
|  | # Joanne Rees-Thomas (JRT) – WAST |
|  | # Joanne Williams (JW) - WAST |
|  | # Joseph Lewis (JL) - WAST |
|  | # Mark Harris (MH) – WAST |
|  | # Olivia Barnes (OB) – WAST |
|  | # Phill Taylor (PT) - WAST |
|  | # Sharon Brown (SB) - WAST |

# Apologies received:

| # Deb Kingsbury (DK) – WAST | # Wayne Lewis (WL) – CTMUHB |
| --- | --- |
| # Colin McMillan (CM) - CVUHB | # Lyndon Powell (LP) - WAST |

Acronyms:

| # ABUHB | # Aneurin Bevan University Health Board |
| --- | --- |
| # BCUHB | # Betsi Cadwaladr University Health Board |
| # CTMUHB | # Cwm Taf Morgannwg University Health Board |
| # CVUHB | # Cardiff and Vale University Health Board |
| # DAG | # Delivery Assurance Group |
| # HDUHB | # Hywel Dda University Health Board |
| # NEPTS DAG | # Non-Emergency Patient Transport Service Delivery and Assurance Group |
| # NCCU | # National Collaborative Commissioning Unit |
| # PTHB | # Powys Teaching Health Board |
| # SBUHB | # Swansea Bay University Health Board |
| # WAST | # Welsh Ambulance Services NHS Trust |
| # WHSSC | # Welsh Health Specialised Services Committee |

| # Item | Agenda | # Actions / Comments | # Further comments | # Attachments |
| --- | --- | --- | --- | --- |
| # 1. | Welcome, Introductions & Apologies # James Rodaway welcomed all to the meeting and all present introduced themselves. Apologies received from staff listed above. DAG Members were also reminded that the frequency of the meetings has now returned to monthly meetings. |  |  |  |
| # Action Notes of Last Meeting |  |  |  |  |
| # 2. | Accuracy and progress against action notes | - Minutes confirmed as accurate (Attachment 1) [JJ 18/08/2020] - Update on Actions: - EASC Risk Register updated to add impact of restarting services for NEPTS - Colleagues were also made aware that the next EASC Joint Committee (8 September 2020) will have a dedicated focus session on ACTION: JR to provide formal update at the next DAG meeting - Action around Cardiac Monitoring can now be closed as discussions have now taken place and concerns addressed with Health Boards. |  | # Attachment 2: Action/Minutes 07 07 2020 |
| # NCCU & WAST Updates |  |  |  |  |
| # 3. | Updates to include: - Update on current position - Proposed Next Steps - NEPTS Demand & Capacity | - Demand & Capacity work progressing well, albeit disrupted by Covid-19. Data has been collected, will some issues around Call Taking data being worked through. Formal update to be provided in due course. - Operational Steering Group has now been set up and held its first meeting last week (14 August). Concerns were raised regarding the lack of Health Board Attendees and colleagues were asked if possible to prioritise these in the diary. Action: Health Board representatives to discuss with Mark Harris for future dates. - Aim to complete the review by end of October 2020, and present back at the November DAG with an update for outcomes of the report. Action: EASC Team to ensure added to November’s agenda. - WAST have appointed the Head of Transformation (Nicola Bowen’s previous role) and hope to start within the next 4 weeks pending recruitment process. All remaining Transfers of Work will need to be progressed at pace (ABUHB, BCUHB, CTMUHB and PTHB). - Workforce Issues: - Demand increasing, but currently struggling with capacity due to the impact of social distancing requirement – having a knock-on effect with efficiency - Shielding has been paused and staff are slowly returning to their previous roles but still significantly having an impact on the service. - Concerns raised from WAST Colleagues, that additional costs may be needed if demand increases and the impact of social distancing continues to reduce vehicle availability. SMH (CASC) emphasises that is it important that we do not conflate the impact of Covid-19 with a more general Demand & Capacity pressure. If pressures is due to Covid then it should be drawn down from the Covid Fund provided by Welsh Government ACTION: Mark Harris to produce paper detailing current status and options available and present to SMH before the next DAG - Renal reimbursement scheme continuing at present, but will need to be revisited to include other enhanced services. Noted that any changes to the eligibility criteria will need to go through a consultation process. - Health Boards are resuming services at different speeds and across multiple locations, and will undoubtedly effect flow and efficiency. MH asked HB’s to keep WAST informed and work together to improve service requirements - DAG members were asked to consider the current Commissioning Intentions 2020/21 as work will be undertaken via the DAG Forum over the coming months to update and refresh for 2021/22. - There will be a focus session on NEPTS at the next EASC Joint Committee (8 September) to give assurance to the EASC Committee on progress made to date. |  |  |
| # Health Board |  |  |  |  |
| # 4. | # Updates to include: - Update on current position (including field hospitals) - Business as Usual developments | # Aneurin Bevan UHB - Contracts Manager has been appointed within the Health Board who will join future DAG meetings – Jennifer Green - Currently engaged in work streams relating to the Grange opening in November 2020. - Work underway to set up and establish Tier 2 & Tier 3 meetings. The aim is to follow the same methodical and structured way the NEPTS DAG adopts moving forward. - Engaged with WAST colleagues to progress Transfer of Work as soon as possible # Betsi Cadwaladr UHB - No patients currently in field hospitals. 1 / 3 field sites are being stepped down at present but will resume if needed - Priority 1 & 2 patients have restarted and will start looking at Priority 3 over the coming weeks. - Outpatient consultations down significantly, with virtual clinics being utilised. - Increase in NEPTs demand particularly in the Wrexham area. - Concerns were raised around health boards booking discharges early enough in the day to support patient flow. - Expressed the need to plan and start the conversation around Transfer of Work and agree timescales. ACTION: JR & MH to set up initial meeting with BCUHB colleagues # Cardiff & Vale UHB - Field hospitals on standby - Spire being used for urgent elective activity - Routine activity now picking up across the health board, with the number of face to face appointments significantly reduced as virtual clinics are increasing. # Cwm Taf Morgannwg UHB - No representation, apologies received. # Hywel Dda UHB - Carmarthen Surge Site operational - Looking at standing down other field hospitals and looking at what potential sites can be restarted quickly if the demand is needed in light of a second wave. - Gradual increase in outpatient activity. - Concerns were raised that NEPTS transport has been unavailable on a number of occasions on the last few weeks which has had an impact on patient flow. ACTION: MH & AE to investigate further and work with GS to address issues. # Powys THB - Working with finance colleagues to progress Transfers of Work - Operational meetings have now restarted with WAST Colleagues - Aim to start increasing outpatient activity (including virtual) in September. # Swansea Bay UHB - Field hospitals currently empty; 1 site has been decommissioned at present. - All Tier 2 & Tier 3 meetings have restarted; positive engagement so far with both WAST & Health Board colleagues and working through a number of issues. - Increase in outpatients activity, particularly around renal and oncology patients (noticed a big shift in enhance service patients) # WHSCC (Renal) - All patient activity has now resumed to normal levels. - Discussions around reimbursement scheme are needed to help reduce pressures. ACTION: JR & MH to discuss restarting project group. - Acknowledged that we need to be mindful that the scheme is not accessible to other patients with lifelong conditions and would collectively need to work with all enhanced services to move forward. # Velindre - Position is largely unchanged. - The key change in the coming weeks will be the recommencing of SACT delivery at the Macmillan Unit at the Prince Charles Hospital in Merthyr. There will be reduced capacity compared to historical norms and, initially, the service will be delivered on three days per week. There is an aspiration to extend this to 5-days, perhaps as early as October. - Discussions are ongoing with respect to the re-opening of SACT delivery and Outpatient services with other health boards. |  |  |
| # WAST – Changes to Booking Processes |  |  |  |  |
| # 4. | # Patient Needs Assessment (PNA): - Proposed changes - Training requirements - Next Steps | - Current PNA assessment is 13 years old, and based on the Welsh Health Circular. - March & May 2020 saw Covid Script updates but overall terminology outdated and have a number of duplications. - Aim to improve overall patient experience and needs both internal & external engagement in order to drive the work forward. - Proposed go live date of 16th September 2020. - Working alongside colleagues within the Community Health Councils to ensure they are kept sighted. - Looking at moving towards online booking that will generate an automatic response and assign booking number. - 5 out of 7 Health Boards have updated websites and patient letters to reflect improvements to the booking processes. # ACTION: DAG members to look through the Attachments 3 & 4 and feedback all comments to Mark Harris. |  | # Attachment 3: NEPTS DAG Covid update – August 15th Attachment 4: NEPTS Eligibility PNA Draft |
| # Innovations & Changes - Workshop |  |  |  |  |
| # 5. | Lessons Learnt - Covid related innovations / changes to sustain - Health Board & WAST pre-work | - 1st September – A workshop will be held to capture the opportunity to develop the insights, innovations and changes made due to Covid-19. Keen to build and sustain the learning and we can take forward post covid. It was agreed to use a future DAG session as a protected hour to work through the details |  |  |
| # AOB |  |  |  |  |
| # 6. |  |  |  |  |
| # Next meeting |  |  |  |  |
| - Tuesday 29 September 2020, 12:00pm - 13:00pm |  |  |  |  |