# Appendix 2

# Extract of Demand and Capacity Review Communications and Engagement Plan

## Updated:  30/08/19

## Action plan

| Phase | Date | Action | Lead | Status |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 | 23/07/2019 29/07/2019 29/07/2019 31/07/2019 | Presentation to EASC WAST Closed Facebook Page WASPT (presentation by DPP) Set up generic email address and place on SIREN (and set up page on SIREN/Intranet) | CASC/CEO AD C&P DPP AC&P |  |
| 3 | 26/08/2019 | Steering Group only. | DPP |  |
| 4 | Early 09 Early 09 25/09/09 23/09/2019 | SIREN Update (about webinars) WAST Closed Facebook Page (about webinars) Webinars x 1 (shift changeover evening) WASPT (presentation by DPP) | AD C&P AD C&P CEO DPP |  |
| 5 | 06/09/2019 10/09/2019 11/09/2019 26/09/2019 Tbc 23/09/2019 10/10/2019 ? Tbc | DoPs – Update on Review EASC – Update on Review WAST EMT WAST Board – Update on Review Specific meeting with WG Senior Decision Makers Welsh Ambulance Service Partnership Team (WASPT) WG Assurance Meeting DoPs – Update on Review EASC Management Group | AD Strategy & Planning CEO/CASC CEO CEO CASC DPP CEO |  |
| 6 | 23/10/2019 08/11/2019 ? 10/11/2019 11/11/2019 ? ? 21/11/2019 Tbc Tbc Tbc | EMT JET WG Assurance Meeting EASC – Final Report and Implementation Plan Webinar x 1 (shift changeover evening) Amber Review Ministerial Statement Collaborative Media Release or Media Lines prepared Trust Board (after Ministerial Statement or closed session) SIREN (after Ministerial Statement) CEO All User Email (after Ministerial Statement) Board of Community Health Councils | CASC CASC CASC CASC CEO CEO CEO CEO DPP |  |

Note: DoF dates to be added (information being obtained).

## Completed communications activity

| Phase | Date |  | Lead | Status |
| --- | --- | --- | --- | --- |
| 1 |  | CEO All User Email SIREN Announcement Establish Steering Group with key stakeholders (TUs, NCCU, HB and WG) Webinars arranged Closed Facebook account created for project manager | CEO CEO AD C&P HofCs Project Support |  |

## Phase Descriptions and Timelines

Phase 1 – Agreement to undertake Review and appointment of supplier (25/06/2019).

Phase 2 – Data requirements, forecasting and base position (29/07/2019).

Phase 3 – Modelling and Interim Results (26/08/2019).

Phase 4 – Draft Results (16/09/2019).

Phase 5 – Final Report (30/09/2019).

Phase 6 – Final Report and Implementation Plan (12/11/2019).