# South Mid and West Wales Trauma Network # Welsh Ambulance Services NHS Trust # Business Case

# Context

## The WAST internal context

Welsh Ambulance Service NHS Trust (WAST) is a critical enabler in the success of the South Wales and South Powys Major Trauma Network.  For the vast majority of patients who suffer major trauma their first contact with NHS Wales will be with the ambulance service when they receive initial care at scene.

The service will also play a critical role in taking these same patients either home following care in the secondary care setting or onwards for their specialist rehabilitation.

The role which the ambulance service is being asked to play within the new network aligns seamlessly with the organisations recently agreed long term strategy for ambulance services in Wales - Delivering Excellence. A strategy which articulates a desire, by 2030 to;

- Ensure quality is at the heart of everything we do;

- Provide the right care, in the right place wherever and whenever it is needed;

- Enable our people to be the best they can be

However the ambulance service will be unable to play this leading role within the network unless it is resourced appropriately.  Whilst the anticipated numbers of patients being cared for within this new model are not expected to change from historic numbers the new clinical model for major trauma will result in the ambulance service making many more ‘new’ journeys, journeys which may often involve significant distance.  Existing resources may be taken out of its local area for much longer period of time.

These longer journeys will also result in some cases, patients needing to be cared for by Ambulance crews for much longer.  This will be a significantly different way of working for our staff and they are going to need support to ensure they can care for their patients as well as they will want to.

Failure to ensure both these aspects are fully acknowledged and commissioned will ultimately result in the erosion of wider operational performance and patients not getting conveyed to the right location first time.

## The wider context

Welsh Ambulance and EASCs 2019/20 Integrated Medium Term Plan both articulate a commitment to develop an All Wales Transfer and Discharge service.

With many more journeys relating to Major Trauma taking place across South Wales and South Powys the establishment of such a service will play a critical role in the success of the network.

However, early funding to support the establishment of this model will also play a role in supporting improvements in wider system flow.  The creation of this model for major trauma will act as a ‘spring board’ to potential further expansion and rollout to support the transfer and  discharge needs of other strategic service changes - most notably the opening of the new Grange hospital in ABHB which will flow circa twelve months after the major trauma network goes live.

## The financial context

WAST makes ongoing commitments within its integrated medium term plans (IMTPs) to be a full and active partner in supporting the successful delivery of a major trauma network for South Wales and South Powys.

However, as a commissioned service through the Emergency Ambulance Services Committee (EASC) our current, and future, plans will stop short of being able to offer assurance on the service being fully funded from an Ambulance perspective until all of the elements of the new service have been agreed and funded by our commissioners.

## 1.4 Definitions

For the purpose of this business case WASTs definitions of the following terms are;

| Repatriation | When a patient is taken from one hospital to another for specialist treatment |
| --- | --- |
| Transfer | When a patient is taken from one hospital to another |
| Conveyance | When a patient is taken from the scene of an incident to the relevant hospital |
| Discharge | When a patient is taken home or nursing home / home of carer |

# Description of the clinical and operational model for WAST

WASTs clinical and operational model that will support the major trauma network will be complementary to the organisations nationally agreed clinical model (below).

Step 2 – Answer my call

All calls which the Ambulance receives via 999 are classified as follows;

The vast majority of major trauma cases will be classified as a red response – immediately life threatening.

Step 3 – Come to see me

Effective pre-hospital decision making will take place within this step and decisions will be taken as to the most appropriate response to send to each case- WAST, EMRTS or both.

This decision process would be facilitated by a Major trauma desk located within the Ambulance Services Clinical Contact Centre (CCC).

It is the assumption of this business case that EMRTS will be a 24/7 service by the time the major trauma network goes live.

Step 4 – Give me treatment

WAST has developed a pre-hospital triage tool in conjunction with the Major Trauma Network, which will be used to support pre-hospital decision making at this step with regard to direct transfer from scene to the MTC in appropriate cases.  Good discussions have taken place with all stakeholders and refinements have also been made to the tool following the peer review workshop on the 13th August.  It is now expected that this tool will be signed off at the major trauma network board in September ‘19

This tool will be supplemented with live clinical decision support of a major trauma desk (see section six) for more borderline cases.

Step 5 – Take me to hospital

Decision taken in step 4 guided by the effective use of the two major trauma triage tools will then determine if in this stage patients are conveyed to the nearest trauma unit or directly to the major trauma centre.

# Overview of governance arrangements

WAST is a full member of the Major Trauma Network Board and has both clinical and planning representation on the group.  WAST has also nominated individuals to all relevant task and finish groups which sit under the network board.

Internally WAST has established a Major Trauma project group which is constituted of all personnel who represent the organisation at the above external boards and task and finishes groups.  This project group will meet monthly until the network goes live on the 01 April 2020.

The following specific governance arrangements have been agreed around the training elements;

Pre-hospital triage tool –the network will ‘own’ this tool.

Responsible – WAST will be responsible for developing the tool

Accountability – Network board will approve the tool. Monitoring of the tool through Network Board on behalf of WHSSC/EASC, however this will require data from WAST on compliance/LHB issues.

Consulted – WAST clinical governance/EMRTS/network governance subcommittee.

Informed – Providers

Online & face to face training

Responsible – WAST will be responsible for developing both of these elements

Accountability – EASC

Consulted – WAST learning and development, network training and education lead, HEIW

Quality Assure – HEIW and EMRTS (as preferred provider)

Informed – Providers

# Phased Implementation

In an approach that is complementary to an underlying principle of the wider major trauma network board WAST is taking a ‘phased approach’ in regards to support of the network.  We are committed to ensuring that the network is safe and effective on the 01 April 2020 and that from this point forward the service will be on a trajectory of continued improvement and maturity.

In this respect our phased approach is outlined below;

|  | Activities | Why | Additional Resource Required |
| --- | --- | --- | --- |
| Essential in place For Day 1 | - Trauma Triage Tools | Supports patients being apparently triaged and conveyed to most appropriate location | See section 5 |
|  | - Online training for staff in relevant geographical areas | Further supports paramedic triage of patients and conveyed of patient to most appropriate location | See section 5 |
|  | - Trauma Support Desk / Expansion of EMRTS Desk to fulfil this function (including recruitment of relevant posts) | Final line of support in triage of patient by offering clinical leadership to on scene paramedics. Ensures most appropriate on scene car is provided and plays a system co-ordination role | See section 6 |
|  | - Agreement on commissioned activity levels for year 1 | Ensures WAST is deploying the most appropriate amount of resources on any given day and that the go live of the network does not destabilise wider WAST operational performance and its ability to attend other non-major trauma cases in the community. | See section 5 |
| Essential in Year 1 | - Commencement and completion of ‘face to face’ staff training - Governance structure in place both network wide and internal to WAST (where relevant) to support decision making. - Transfer and discharge service |  | See section 7 |
| Essential in Year 2-3 | - Ongoing data collection - Dedicated EMRTS vehicle |  |  |
| Essential in Year 4-5 | - Ongoing data collection |  |  |
| Desirable & aspirational goals | It is desirable for some face to face training to begin prior to go live |  |  |

# Any additional resource requirements for increased ambulance journey’s, based on the attached dataset signed off by network board (Figure 7 and the section on ‘care closer to home’ and any local HB work undertaken (e.g. Hywel Dda).

WAST have identified that the development of a major trauma network will have a significant impact on its resources.  In beginning to quantify and understand these implications a number of existing policies, Welsh Health Circulars and agreed stances of Emergency Ambulance Services Committee (EASC) have been considered.  These include;

- WHC (2017) 008 NHS Wales policy for repatriation of patients

- Designed for Life Welsh guidelines for the transfer of the critically ill adult

- Developing a Once for Wales approach to quantifying the impact of Health Board strategic service changes (26 June 2018)

In noting the documented implications on the Ambulance service in this paper it is important to note that it has been necessary to use a number of assumptions over and above those used in the production of the Predicted data activity for the Wales Trauma Network v0.8 (May 2019) paper which is the basis of the whole networks board planning.

Individual assumptions which have been used for particular areas are clearly documented within the relevant section of this paper. An Executive decision of the organisation was taken that where assumptions need to be used that ‘worst case scenario’ assumptions should be used.

In light of this it is highly recommended that after year one of the service when accurate ‘actual’ activity has been collected that further commissioning conversations are held regarding pre-hospital conveyance, secondary conveyance, repatriations and follow up rehabilitation activity.

## 5.1	Emergency Conveyance Times (job cycle times)

The implication here derives from the fact that traditional suspected major trauma cases would have been conveyed from scene to the nearest appropriate hospital.  The new model will see the patient conveyed either to the nearest Trauma Unit (TU) or direct to the Major Trauma Centre (MTC) at the University Hospital of Wales, Cardiff (UHW).

Assumptions

- NHS Wales is collectively unable to determine exactly where suspected major trauma incidents take place.  To mitigate this an assumption has been made that they all happen at the hospital site to which they would have been conveyed under the existing model. This is clearly not reality.

- Because existing incident locations are not known existing conveyance distances/times have not been able to be deducted to understand the ‘new’ element of activity.

- HDHB are currently consulting on the status of Bronglais and Withybush hospitals within the new model.  Whilst it is proposed that both sites become designated rural trauma facilities given this is not yet agreed and the granularity of detail as to what this actually means is also not yet known the assumptions adopted in this paper remain that all forecast activity for these hospitals will initially be conveyed to Glangwilli only.

- It has been agreed between WAST, EMRTS and office of the CASC that there should be no attempt to split the total activity requiring conveyance between WAST and EMRTS and that instead it is clinically appropriate to model on the basis that WAST will have a role to play in all initial 999 major trauma calls.

## 5.2 Secondary transfers (transfer from TU to MTC)

The implication here for the ambulance services derives from the fact that in some cases it will be appropriate for the patient to be conveyed to the MTC via a TU, for stabilisation for example.

Within the traditional model it would have been unlikely for the patient to have ever been moved from the destination of their first conveyance thus this represents new activity for WAST.

## 5.3	Repatriations (back to TU and/or patients local DGH, to specialist rehabilitation site, home or home of a carer)

Whilst repatriations will have been a feature of current service provision there are ‘new’ implications for WAST in that there will now be a greater number of people in UHW that will now need repatriation.

Assumptions

    - Whilst some data exists to project the proportion of patients who will pass away whilst in UHW and some whom will require repatriation or transfer to specialist rehabilitation sites (and thus these numbers are built into modelling).

    - No data exists to indicate that when a patient is ready to be discharged home / nursing home / home of carer etc. how they return to these places. It has therefore been assumed that WAST will undertake all of these discharges.

    - In addition to the above existing places of residence and other key data information which determine where patients might need to be conveyed does not exist thus modelling is always based back to a local DGH. This will not reflect reality.

    - A lack of data means it is not possible to understand existing repatriation distances/times and to deduct it in order to understand the ‘new’ element of repatriation activity.

    - Repatriations will be undertaken by WAST UCS and NEPTs crews in line with existing NHS Wales policy.

Key risks and Issues

As work continues with Morriston hospital to determine what acuity of patient it can treat as part of being an ‘enhanced’ trauma unit this could affect the quantified implications for the Ambulance service.

At the time of submitting this business case conversations continue regarding ‘Orthoplastics’ flow to this site. Suggestions are that the majority of cases are already going there directly (with EMRTS response road or air) but this has not yet been qualified by the Ambulance service and if proven not to be the case could have a material impact on patient flows with, for example, a Newport (Gwent) patient being triaged to Morriston.

As part of approving this business case commissioners should be aware there will be a requirement to review this situation retrospectively.

# Staff Training

## Background and Proposed Approach

The system of major trauma networks proposed for South Wales will require patients with identified injuries to be transported to the major trauma centre. A triage tool (and where necessary silver triage tool) would be used to identify patients who fall into the major trauma category and these patients would be taken directly to a Major Trauma Centre for optimal care.

This may require WAST EMS staff to manage patients with serious traumatic injuries for longer periods of time. This will require training of the management of trauma patients using the current trauma equipment supplied by WAST.  It will also be necessary for staff to undertake training in utilisation of the pathway and familiarisation with the Trauma Network.

Whilst many of the organisations Emergency Medical Service (EMS) colleagues get 52 hours CPD time, others receive less (it is hoped that this allocation will be standardised across all staff in this group once an internal roster review exercise has been complete).  In addition there is a long standing agreement with the organisations trade union partners that only fifteen hours of total CPD time is ‘directed’ by the organisation

The organisation recognises that the annual CPD programme for WAST colleagues would usually be the best option for delivery of such training, however, the directed fifteen hours’ time for the next year has been ring-fenced for the Band 6 education process (which has been planned since 2017) and other standard mandatory training which staff are required to undertake.

Mandating staff to also use their CPD hours for the required major trauma training would require detailed conversations with our trade union partners to extend the number of CPD hours which the organisation currently ring-fences.  Early discussions with trade union partners have begun but at this moment in time negotiations are ongoing.  This business case is therefore predicated on the assumption that CPD hours cannot be utilised as this represents the worst case scenario financially for commissioners to plan against.

WAST is the only provider of emergency transport in Wales, operating in a complex environment in terms of geography and topography. Whilst the establishment of the South Wales Trauma Network presents many benefits and opportunities, it should be recognised that it compounds already existing service delivery challenges. We must ensure that our practitioners are fully equipped in terms of decision making and clinical intervention skills to fully support this initiative.

WAST currently operates from 105 sites across Wales meaning that education and training of colleagues is not a straightforward and simple task. It is important that we recognise and utilise the expertise of EMRTS colleagues in relation to trauma in order to ensure quality of learning. Support is therefore required from EMRTS colleagues in relation to delivering Train the Trainer sessions for our staff and quality assurance of our delivery.

Potential delivery options have been reviewed in collaboration with the Consultant Leads for the Major Trauma Network and the preferred option is set out below:

- All colleagues complete the eLearning module (1 hour) by 31st March 2020. This learning will be provided in workbook format for those colleagues who require it

- EMRTS have agreed to carry out ‘Train the Trainer’ training and quality assurance for WAST as part of their business as usual. Following this colleagues will then receive a 1 day (7.5 hours), face to face Trauma Network training session delivered by the recruited trained WAST tutors. These roles will need to be filled on a secondment basis, as the existing small Education and Training delivery team in WAST is fully committed to a challenging workforce / training plan. Additionally, there will be a need to recruit a Trauma Network Lead Tutor to oversee delivery, recording and reporting (please see Fig. 1 below for details of team).

Fig. 1

The team would comprise:

- 1 x Lead Tutor (responsible for overseeing project delivery and reporting and delivery of training) – 12 month secondment at band 7

- 3 x Tutors (responsible for delivery of training) – 3 x 7 month secondments (delivery of South Wales training) and 3 x 5 month secondments (delivery of Mid and North Wales training) all at band 7

WAST recognises that whilst the face to face training is a one-off cost it will still represent a significant investment from the wider system which commissions Ambulance Services in Wales.  Detailed conversations have taken place not only internally but also with the network board, commissioners and through the external peer review exercise as to the most appropriate way to roll out this training.  Discussions allowed three options to be considered;

- Do nothing – have no face to face training.

- Conduct face to face training of all staff during 2020/21 with a prioritisation of staff in the most geographically important areas of Wales during quarter 1

- Phase training over three years with a prioritisation of staff in the most geographically important areas of Wales during 2020/21

Option one was immediately discounted because of the significant impact of quality of service provision and the wider implications this would have for the success of the network.

A SWOT analysis of options two and three were subsequently undertaken (see annex 5).  This has resulted in option 2 being the preferred option.

In summary this SWOT analysis confirmed that the totality of the required investment cannot be reduced and any phased approach to the delivery of training possess a disproportionate level risk to the success of the network compared to any benefits of spreading the cost of training over three years.

Training in year one will still be prioritised according to geographical complexity, i.e. recognising the challenges faced by colleagues in Hywel Dda and South Powys (longer journey times).

Timelines for training can be found in Annex 3 although it is still recognised that some face to face training may be able to be achieved prior to go live in year, if the wider system wishes to release in year funding to support this.

Whilst BCU and North Powys staff are already operating within an established English trauma network it is important that the service equity principles described in A Healthier Wales are ‘lived’ and that Ambulance staff operating in North Wales ultimately receive the same training as colleagues in the south so that they can continue to offer the best possible care to the people of North Wales.

Benefits of this approach:

- Timely delivery

- High quality training

- Appropriately skilled workforce

- Existing training plan is not adversely affected – ensure business continuity

- Enhanced trauma management skill set for colleagues across Wales

- Fully supports the Trauma Network initiative

As an organisation we work closely with our staff representatives and consequently we know what works and what does not work so well.  As mentioned above our staff are geographically dispersed across Wales but also, in addition, are collectively a very different demographic from perhaps many other clinical workforces in Wales.  A high proportion will not be IT literate or have experience in accessing clinical training online and/or remotely thus the face to face training is an important ‘safety net’.

The ‘face to face’ exercise is also a very important opportunity for the organisation to win the hearts and minds of its clinical workforce and ensure that the principles and aims of the wider major trauma network are instilled within staff mind-sets and they see an understand the true value of embracing the networks way of working and not merely defaulting to existing working practices.

As part of the peer review exercise undertaken on the 13 August we have taken advice to evaluate the effectiveness and uptake of the proposed training at appropriate intervals.

ONLINE TRAINING

Our preferred supplier is Onclick as WAST is already using this company for other eLearning. Onclick are building a very good portfolio of eLearning packages and remain competitive in this field. Our operational and training teams are currently working through the training programme and elements needed to be included and ensuring it meets the requirements of EMRTS and revises the concept of the trauma network, the use of the triage tool and the role of the desk, as well as the trauma care concepts and equipment focussing on high risk key interventions. (Our timeline to rolling out the eLearning can be found in Annex 2).

COSTS

ELearning

Costs associated with the e-learning focus on the design and development of an interactive Major Trauma Triage tool, for installation on the WAST Learnzone. This will include instructional design and copywriting of content, custom graphic design and eLearning build.  In addition a bank of multiple choice, case study-based assessment to be built within learning platform, with certification on successful completion. Further signposting and resources to be embedded within WAST Learnzone. Scheduled report to be set up for WAST and South Wales Trauma Network. £8,100

Duration of eLearning = 1 hour

Backfill costs (at time and a half) for eLearning: £35,969

- Paramedics (band 6): 949 @ £27.48hr = £26,078

- APPs (band 7): 19 @ £32.93hr = £626

- AEMTs / EMT3s (band 5): 92 @ £23.84 = £2,193

- EMT1 / EMT2 (band 4): 374 @ £18.91 = £7,072

We will be working with OnClick to ensure monitoring of our staff compliance and following a recommendation from the Professional Peer Review will be aspiring to achieve a minimum 70% trust wide compliance at ‘go live’ with an increase to 85% by three months in.

Face to face

Total number of staff to be trained: 1434

- Paramedics (band 6): 949

- APPs (band 7): 19

- AEMTs / EMT3s (band 5): 92

- EMT1 / EMT2 (band 4): 374

For the purpose of this business case we have costed for all EMS staff to be trained assuming that they all might need to use and initiate the major trauma triage tool and use relevant trauma skills to transport patients further to the major trauma centre at some point. Only providing the training to Paramedics would leave us ‘at risk’ as we operate double EMT crews on occasions and APP’s are sometimes operating as paramedics operationally e.g. Clinical HB Leads or on an overtime basis at periods of high demand.

Delivery costs: £200,781.74

- 1 x Lead Tutor (band 7) x 12 months = £50,195.43

- 3 x Tutors (band 7) x 12 months (this would comprise 3 x 7 month secondments and 3 x 5 month secondments) = £150,586.30

As this learning will be undertaken by a separate team of educators predominately at venues close to the learners and not at WAST normal training bases, they will need to be self-sufficient and not reliant upon the existing training equipment held at the WAST training centres.

Also WASTs existing training equipment may need to be used to maintain business as usual and therefore not available for the Trauma Network training sessions which could hinder the role out. Therefore the following equipment would be required;

Equipment costs: Total approx. (incl. VAT): £31,171

4 x Windows based laptops					approx. = £3,200.00

4 x Multimedia projector					approx. = £2,000.00

4 x RSA SecurID						approx. = £320.00

4 x Airway Management Trainer				approx. = £6,560.00

4 x Cricoid stick Trainer					approx. =£2,505.60

4 x Chest Decompression Trainer 				approx. =£4,272.00

8 x Quicktrack II airway device				approx. = £1,248.00

8 x Pneumofix chest decompression device		approx. = £200.00

12 x WAST trauma packs					approx. = £960.00

4 x Kendrick traction splints   				approx. = £236.00

4 x Pelvic splints						approx. = £152.00

4 x EZ IO Training Kits					approx. = £1,000.00

2 x Trauma Manikins						approx. = £3,318.00

There has been a robust internal exercise to review the equipment requirements for this face to face training and we have satisfied ourselves that this ask of the training department is fair and proportionate.  Included within annex 3 is a copy of a draft agenda of the training day to support evidence as to how and where equipment will be utilised

Travel costs (tutors):

£458 x 4 tutors x 12 months = £21,984

(This figure of £458 per month is based on mileage costs associated with delivery of the Band 6 education process)

Backfill costs (at time and a half) for face to face: £269,768

- Paramedics (band 6): 949 @ £27.48hr  x 7.5 hrs = £195,585

- APPs (band 7): 19 @ £32.93hr x 7.5 hrs = £4,695

- AEMTs / EMT3s (band 5): 92 @ £23.84 x 7.5 hrs = £16,448

- EMT1 / EMT2 (band 4): 374 @ £18.91x 7.5 hrs = £53,040

Dependencies

This training requires the full support of WAST operational teams and resource departments to ensure staff attendance to maximise educator to student ratio.

Support is required from EMRTS in terms of Train the Trainer delivery and quality assurance.  This support has been indicated from the organisation.

Support from Area Managers (WAST) is required in relation to accessing suitable teaching spaces at existing WAST sites.

The model requires full support of WAST Operations Directorate to release 4 x colleagues to facilitate this training (Lead Tutor and Tutor roles) on a secondment basis.

Full support from the Clinical and Medical Directorate is required, in terms of provision of advice, guidance and support from Health Board Clinical Leads / Consultant Paramedics.

Support from and collaboration with Trade Union partners is required, as well as engagement from staff.

Key Risks and Issues

- Failure to secure commissioning for the face to face element of the training:

Should funding not be secured for the face to face element of staff training there is an increased risk that staff do not understand and/or buy into the opportunities and benefits  which a high quality major trauma network can bring.  As such there is an increased chance that a proportion of staff maintain existing working practices and take patients to inappropriate locations.  This will affect not only patient outcomes but also the flow assumptions of the network.

- Success is dependent on availability of funding and allocation in a timely manner.

It is anticipated that a commissioning decision may not be taken until September 2019 when the Emergency Ambulance Services Committee (EASC) meets.  Should a timely decision not be made at this meeting there runs the risk that the minimum number of, and highest priority staff, may not receive the required training before the network goes live.

The estimated implication for training is assumed to be a non-recurring cost of;

£567,774

# The Major Trauma Desk

Recognising the vital role the trauma desk will play in supporting the network, from patient distribution through to support of crews and mobilisation of EMRTS critical care resources it has been agreed this is essential for ‘go live’.

The desk will be staffed by appropriately trained and experienced senior clinicians which will give expansive depth and breadth of function. This will include;

- Scrutiny of calls on the CAD to target appropriate resources to likely major trauma and critically ill patients. This will require very close cooperation with the EMRTS clinicians to optimise appropriate resources to scene;

- Carrying out call backs on calls that may identify major trauma patients to gain additional information that may improve triage of appropriate resources, again in conjunction with EMRTS;

- Play a vital role in supporting WAST crews in decision making around destination hospital and clinical advice to support the possible distance transfer and be the final arbiters in the decision to transfer patients to the MTC or other facility;

- Assist in pre-alert and notification of major trauma cases to MTC or MTU;

- Support delayed primary transfer for those patients who have had to pit-stop at an MTU due to instability. This will also be in conjunction with EMRTS support for critical care transfer.

The screening of calls through the Major Trauma desk along with the tightness of the triage tool will hopefully reduce any potential over triage to the MTC to an appropriate level.

In order to accommodate the desk and for step two of our clinical model to operate as effectively as possible in the context of major trauma, new arrangements within WASTs clinical contact centres (CCCs) and current working arrangements with the existing EMRTS air desk have needed to be considered.

A field visit to the West Midlands Ambulance Service Air desk, who have been supporting their major trauma networks for five years, was carried out in May 2019.

Options considered included:

- The status quo.  No changes to existing practices and should paramedics on scene have queries regarding a patients suitability for conveyance to the MTC then dialogue directly with on-call MTC consultants takes place.

- There is suitable expansion of the EMRTs air-desk in order for this service to co-ordinate the pre-hospital element of the network.

3a.	The creation of a separate ‘WAST’ major trauma desk which works coterminously with the existing EMRTS air desk, is staffed by a band 7 clinician and operates 24/7/365.

3b.	As above but with a reduced operational hours. 14/7/365 (hours of the day being 0800-2200) and the function ‘falling back’ to the EMRTS desk out of hours.

4a.	The creation of a separate ‘WAST’ major trauma desk which works coterminously with the existing EMRTS air desk, staffed by an additional allocator band 5 role and operates 24/7/365.  Here the clinical decision making would rest with the EMRTS CCP on the desk with the band 5 freeing up CCP to make the clinical decisions, rather than undertaking non-clinical communication duties.

4b. As above but with a reduced operational hours. 14/7/365 (hours of the day being 0800-2200) and the function ‘falling back’ to the EMRTS desk out of hours.

Option 3b has been identified as the preferred option;

The is the creation of a separate ‘WAST’ major trauma desk which works coterminously with the existing EMRTs air desk, is staffed by a band 7 senior paramedic and operates 14/7/365 (hours of the day being 0800-2200) and the function ‘falling back’ to the EMRTS desk out of hours.

A SWOT analysis which summarises the decision making process is shown in annex 4. In reaching this preferred option the following points of the SWOT analysis were considered critical;

- The desk needed to be appropriately resourced so that the existing EMRTS Clinical Care Practitioner (CCP) did not experience an experiential rise in workload. Specifically, potential queries from on scene paramedics and the application of the major trauma triage tool.  This necessitated that staff has to be at band 7, senior paramedic level

- The configuration of any desk should ‘future proof’ itself so that it could suitably support other strategic developments potentially happening across NHS Wales. For example the developments planned in critical care as a result of the £15m investment into the service by the minister.

- Current data and predicted demand does not suggest that a 24/7/365 trauma desk offers value for money and that high quality and safe care can be provided directly by the Air Desk between the hours of 2200 – 0800.

EMRTs have confirmed that they are supportive of this preferred approach and it is recognised that the working relationship with the air desk staff is vital to the success of the desk.

To support the operation of the WAST Trauma Desk it’s is essential that the clinicians maintain their clinical skills within a face to face role. Therefore, to facilitate this rotation between the Trauma Desk and operational setting, it is vital to create capacity in the clinician’s roster hours to enable patient contact and the maintenance and develop of clinical skills.  Therefore whilst draft versions of this business case have shown a necessity for 3.48 WTE this has been scaled up to 4 WTE to allow the aforementioned rotation.

In addition it has also been identified that to ensure the desk is providing an effective and safe service on the 01 April that it will be necessary for staff to have an element of additional training this will include operating in a ‘shadow’ environment for a period of time prior to go live as well as training on the systems. (The planned approach and timelines for this approach can be found in Annex 2).  This business case therefore now identifies four months in year (2019/20) staff costs to facilitate this.  The importance of this pre-live training and shadow form operation was again some helpful learning taken from the peer review exercise.

Key Risks and Issues

It is recognised that the banding of the WAST member of staff on the Trauma desk may create some initial disparity with the EMRTS CCP role which operates on the air desk.  However it is important to recognise that CCP’s only operate at a band 6 whilst they are undertaking their MSc qualification and upon completion of the course are then remunerated at band 7, thus creating parity.

Discussions have taken place with EMRTS on this issue and the service have confirmed that this is a situation that can be managed.

In confirming the preferred option for a major trauma desk it is noted that a key assumptions adopted is that the EMRTs service gets the required funding and subsequently launches its own 24/7 service.

The estimated revenue implication for staff is therefore assumed to be;

£266,452.60

# Transfer and discharge model

With many more journeys relating to Major Trauma taking place across South Wales and South Powys the establishment of a function to effectively and efficiently co-ordinate these journeys will be critical.

An expanded additional call handler/dispatcher resource will provide the required capacity to ensure the safe delivery of journey co-ordination.

However, the need for an effective and efficient co-ordination of journeys function is not limited to the changes planned for major trauma.  It will play an equally critical role in the success of other strategic developments across NHS Wales such as the opening of the Grange Hospital in AHBHB.

In recognising this both the WAST and EASC IMTPs make the commitment to develop a proposal for All Wales Transfer and Discharge service within 2019/20.

The creation of the major trauma network in South Wales and South Powys has been identified as being the ideal ‘spring-board’ for the potential creation of this test service that can be trialled and evaluated prior to wider rollout across Wales.

The estimated revenue implication for an initial transfer and discharge service for major trauma is assumed to be;

£122,530

A wider piece of work is being taken forward by WAST, CASC and Health Boards to determine what the preferred model could look like.  However for the purposes of this business case an assessment has been made as to what funding maybe required to support transfer and discharge service for major trauma.  The figure represented in the business case for this part of the service represents the additionality in activity that is forecast to be created by the network.

# Financial Summary

|  | Recurring Costs |  | Non-Recurring Costs |
| --- | --- | --- | --- |
| Collective revenue implications for conveyances, secondary transfers and repatriations or discharge. These figures, as described in this paper, are based on ‘worst case scenario’ modelling. Following a year’s operation of the network ‘real’ data will have been collected meaning a review of projected costs for years 2, 3 and beyond can be undertaken. | Year 1 | £244,388 |  |
|  | Year 2 | £245,689 |  |
|  | Year 3 | £250,525 |  |
|  |  |  | Total £567,774 |
| Staff for Major Trauma desk | **2019/20 | £57,954 |  |
|  | Subsequent Years | £266,452.60 |  |
| Staff for Transfer & Discharge service for Major Trauma | £122,530 |  |  |
| Overall Cost Year 0 | £57,954 |  |  |
| Overall Cost Year 1 | £1201,144.60* |  |  |
| Overall Cost Year 2 | £634,671.60 |  |  |
| Overall Cost Year 3 | £639,507.60 |  |  |

* A proportion of this training cost could be bought forward to 2019/20 should a timely commissioning decision be taken meaning training can be mobilised earlier than indicatively planned.

** This cost for 2019/20 will cover the Major Trauma Desk staff starting in January 2020 allowing them time to shadow EMRTS and undertake sufficient training ready for go live as recommended at the Network Board.

In parallel to the development of this business case WAST is also developing a new ‘senior paramedic’ role which would operate at a band 7 role.  The potential to include duties on the Major Trauma desk are currently being explored. If this is not determined to be the best approach then a further ‘bespoke’ role will be developed.