| CAREMORE Plan on a Page: Emergency Ambulance Services Collaborative Commissioning Framework Agreement – enhancement for 2022/23 – 2024/25 STATUS V8 10.08.22 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Care Standards | Activity | Resource Envelope | Model |  | Operations |  | Review |  |  | Evaluate |
| Product: An evidenced set of care standards for Emergency Ambulance Services to ensure that the right expectations are defined for quality and safety. | Product: An accurate description of the activities within Emergency Ambulance Services to ensure that the right capacity is available to meet the right demand. | Product: A comprehensive description of the assets which may be utilised and affected with the ambition of making the best use of all existing resources. | Product: A common high level model of care for Emergency Ambulance Services to ensure that people can access the right staff, at the right place, at the right time. |  | Product: The establishment of robust local mechanisms to ensure effective delivery with the right interaction between patients, professionals and organisations. |  | Product: An agreed system of performance measurement to ensure the right monitoring and management to deliver continuous improvement. |  |  | Product: An agreed set of methods and criteria for judging the achievement of the right patient outcomes, from the right patient experience, at the right cost. |
| Schedules (within each Section of the framework) |  |  |  |  |  |  |  |  |  |  |
| C1 Care Standards (June 2022 V1) | A1 Activity Descriptors (June 2022 V0.1) | RE1 Resource Management Descriptors (June 2022 V0.1) RE2 Joint Annual Financial Management Control Plan (June 2022 V0.1) | M1 Model of Care Descriptor (June 2022 v1) |  | O1 Integrated Commissioning Action Plan Blueprint (June 2022 v0.9) O2 Putting Inverting the Triangle into Practice Tracker (June 2022 V1) |  | R1 Performance Descriptors (June 2022 V0.1) R2 Repository of Activity Resources Performance & Reporting (to be drafted) |  |  | E1 Evaluation Methods (July 2022 V1) |
| Ongoing Developmental Work |  |  |  |  |  |  |  |  |  |  |
| - ACTION TAKEN: C1 – Care Standards across each step of the patient care pathway to remain extant until where are we now (current positions) across WAST & Health Boards are gathered as part of Integrated Commissioning Action Plans – which may lead to their updating [C1 Owners: RW SA] | - ONGOING ACTION: A1 – AQIs to continue alongside exercise to: - map extant AQIs against Care Standards (specifically identify activity related measures) - reflect upon utilisation, learning & experiences to date from reporting AQIs - develop specific data sets to support shift towards Inverting the Triangle [A1 Owners: ASQI Group RW HB RT] | - ONGOING ACTION: RE1 – AQIs to continue at present with - Exercise [A] to: - map extant AQIs against Care Standards undertaken (specifically identify resource related measures) - reflect upon utilisation, learning & experiences to date from reporting AQIs - develop specific data sets to support shift towards Inverting the Triangle - Exercise [B] review & update if required previous Resource Management descriptors. [RE1 Owners: ASQI Group RW RT JC] - ACTION TAKEN: RE2 – built upon previous versions and includes: details of the financial plans across EASC & WAST; any requirements for funding to be released & associated responsibilities; expectations from ‘additional’ funding & impact upon control WTEs for specific staff groups - ONGOING ACTION: RE2 being spreadsheet being finalised by JC plus commitment to service line reporting intentions [RE2 Owners: WHSSC SMH RW & JC] |  | - ACTION TAKEN: M1 – Model of Care descriptor to remain extant alongside current Care Standards which may be updated following understanding of where are we now (current positions) across WAST & Health Boards [M1 Owners: RW SA] | - ACTION TAKEN: O1 – Blueprint produced - ONGOING ACTION: O1 – As per separately provided Implementation Plan for creation of LHB Footprint specific Integrated Commissioning Action Plans [O1 Owners: SMH RW ME] - ACTION TAKEN: O2 – Tracker produced - ONGOING ACTION: 02 – Tracker to be regularly updated [O2 Owner: ME] |  | - ONGOING ACTION: R1 – AQIs to continue at present with exercise to: - map extant AQIs against Care Standards (specifically identify performance measures) - reflect upon utilisation, learning & experiences to date from reporting AQIs - develop specific data sets to support shift towards Inverting the Triangle [R1 Owners: ASQI Group RW RT] - ONGOING ACTION: R2 –Following completion of the exercise underway to update the AQIs as referenced above there is then the requirement to identify the key data sets for each Board, Group or Forums which have a performance management role in relation to both EASC and WAST across the organisations themselves, and more broadly NHS Wales and the Welsh Government [R2 Owners: ASQI Group RW HB RT] |  |  | ## ACTION TAKEN: E1 – Reviewed Evaluation Methods for EDQDF to consider elements of approach which could be applicable to emergency ambulance services; Highlighted Quad Aim relationship with extant Care Standards to support data gathering for evaluation; Referenced development of Patient Public Involvement Group and qualitative study in support of HIW Handover report recommendations ## ONGOING ACTION: E1 – Determine evaluation work programme which could be based upon initiatives identified from the LHB Integrated Commissioning Planning Process ## [E1 Owners: SMH RW SA KJ] |
| Current Workplan |  |  |  |  |  |  |  |  |  |  |
| Care Standards | Activity | Resource Envelope |  | Model |  | Operations |  | Review | Evaluate |  |
|  |  |  |  |  |  |  |  |  | EDQDF Evaluation Methods Schedule |  |