Six Goals for Urgent & Emergency Care: Highlight Report

Goal 4: Rapid response in a physical or mental health crisis

| Author: Sian Ashford |  |  |  | Previous RAG Rating: | Overall RAG Rating: |  |
| --- | --- | --- | --- | --- | --- | --- |
| Submission Date: 15/08/2023 |  |  | Period covered: Qtr 1 23/24 |  |  |  |
| Goal 5: Key Deliverables 22/23 |  |  |  |  |  |  |
| Workstreams | Current RAG | Workstream Progress | Key Activities & Achievements | Priorities for Next Period |  | Performance Trend |
| Optimising Response |  | Connected Care Cymru scoping work Full roll out of CHARU commenced All Wales roster reviews completed | Future D&C model Commissioned Review of Remote Clinical Support underway Red Improvement plan progress | Continue to deliver priorities in EASC action plan and ICAPs |  |  |
| Optimising Conveyance |  | Multiple ambulance Flow/Navigation models now in operation across Wales Continued us of mental health transport service provided by St John Review of APP perfect days underway | Incident and Conveyance Review linked to Welsh Deprivation index UCS, T&C Demand and Capacity models underway | Continue to deliver priorities in EASC action plan and ICAPs |  |  |
| Data gathering / digital improvements |  | Getting it Right First Time (GIRFT) to identify unwarranted clinical variation using The Summary Emergency department Indicator Table (SEDIT). Exploratory work underway to understand what data is available at each health board. Information reporting group meeting in 17 May chaired by Simon Jones | GIRFT – Deep dive into what data is available across all UHB’s in development, (to be completed by end of June). AA draft ToR and project plan will be taken to next Information Reporting Group in June. E-Triage- Devices ready for deployment | GIRFT- Continue gathering data, update in September E-Triage – dates for ‘go live’ secured, gather learning and review impact in Q2 |  |  |

| ED Improvement |  | Previous ED improvement initiatives being reviewed and an updated plan in development with Clinical Lead. Endorsement of Emergency Medicine Quality Statement development Continuous Flow Model | EDQDF has identified some good learning opportunities, we will use these opportunities and develop revised priorities for ED improvement Task and Finish Group stood up, communication and engagement plan created Engagement / endorsement from each ED clinical lead and lead nurse. Discussions at wider clinical and NHS leadership groups ongoing. Event – ED leaders gathered to discuss next steps for ED element of Goal 4. Southmead clinical lead presented CFM which was well received. | Meeting with local ED leaders, gathering confidence and building network. Explore opportunities for improvement by visiting other areas. Continued stakeholder engagement Goal 4 Board Task and Finish sub group of Goal 4 stood up (first meeting in Aug) Initially working with Swansea Bay to understand implementation of a new model (Q&A session with staff in Aug), gather learning and evaluate impact. Other sites to follow soon after (consideration being given to GUH and YWM) |  |
| --- | --- | --- | --- | --- | --- |
| Escalation |  | National Escalation Framework signed off by senior leaders and ready for team engagement and deployment. | National system wide escalation framework created. COO Group stood up to assist with review and implementation | Review resources and scope implementation plans Continue to work with Goal 4 sub Group (COO’s) to review framework and discuss implementation plans |  |
| Additional Workstreams – Not listed under latest plans on a page |  |  |  |  |  |
| Workstreams | Current RAG | Workstream Progress | Key Activities & Achievements | Priorities for Next Period | Performance Trend |
| Integrated Commissioning Action Plans (ICAP’s) |  | ICAP process established, relationships built, structure in place. Versions 1 of ICAP created, discussed at local levels and initiatives input by UHB’s and WAST to create version 2 and 3. | The structure of ICAPs is now established resulting in refined membership and version 4 of ICAPS updated. | Production of version 5 of ICAPS |  |
| Review of the remote clinical assessment of 999 calls |  | Terms of reference set, meetings with stakeholders arranged | Further data gathering exercises underway | Completion of report by end of Aug 2023 |  |

| Performance Measures & Metrics (In place, or to be defined) | Additional Comments |
| --- | --- |

| Six Goals Risk Register |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description of the Risk | Effect | Initial Risk Score |  |  | What has been done to manage the risk to date? | Current Risk Score |  |  | Change from previous | Additional Risk Action / Treatment | Flag to Board (Y/N) |
|  |  | Consequence | Likelihood | Score |  | Consequence | Likelihood | Score |  |  |  |
| Actions in ICAPS are dependent on funding and resource availability | If WAST / UHBs do not have the resource to deliver the initiative this will impact upon flow, patient experience, clinical outcomes and value. | 4 | 4 | 16 | Aligns to IMTP ambitions, raised through management group and joint committee | 4 | 4 | 16 | n/a | Regular ICAP meetings to update on progress | Y |
| Lack of resources to deliver Goal 4- ED improvements / Escalation Framework | Limited improvements impacting clinical outcomes, experience and value | 4 | 5 | 20 | Business case developed to request funding for resource support | 3 | 4 | 12 | n/a | Business Case submitted | Y |
| Unwarranted variation around Health Board executive ownership and use of ED triage and assessment data to enable service improvement | Variation in time to triage across Wales which could mean variable patient experience and outcomes by site / UHB | 3 | 5 | 15 | OD piece around GIRFT may mitigate this eventually but opportunities may be being missed due to a lack of health board ownership | 3 | 5 | 15 | n/a | To be raised with each health board as part of ICAPs | Y |